Project Monitoring and Control

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 4-Nov-14 |  | NA | Initial Version |
| 1.0 | SEPG | 26-Nov-14 |  | NA | Initial version |

Purpose:

The purpose of project monitoring and control procedure is to

- Track all planning parameters

- Provide adequate visibility into actual progress results against planned

- Ensure identification and implementation of corrective actions for any variation in planned parameters

| Inputs | Outputs |
| --- | --- |
| - Org Level Project Management Plan - Project Level Project management plan (PMP) - Project in PMS tool - Project schedule | - Update PMS tool - Project Progress Report - Senior management review report - Minutes of Meeting from reviews - Filled Process Compliance checklist - Audit Report |

Entry Criteria:

- Baselined Org level project management plan

- Baselined Project level Project management plan (PMP)

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Project Manager | Plan The Tasks | Project manager plan the tasks in PMS tool and allocates the task to all the team members |
| Project Manager | Track Planned Parameters | Project manager update the PMS tool for schedule, effort, defects based on the inputs from team members Project manager monitor and tracks - Effort, Schedule, Defects and other Metrics data performance - Cost - Risks in the project - Staffing plan - Issues, assumptions and dependencies - Other planned parameters Project manager updates PMS tool during every phase and at every phase end. Project Manager shall log and track issues, assumption, dependencies in PMS tool |
| Project Manager | Escalate The Issues And Dependencies | If required, project manager escalate the issues and dependencies with relevant stakeholders (as applicable), in consultation with HOD. Project manager will log all The issues in PMS tool and actions will be tracked to closure |
| Project Manager | Review Project Progress | Project manager periodically (as per review frequency defined in Org level PMP) reviews status with team during project progress review meeting. |
| Project Manager | Conduct Senior Management Review | Project manager periodically (as per review frequency defined in Org level PMP) review status of the project with HOD. Project manager prepares MOM and share with relevant stakeholders and track action items to closure. |
| Project Manager | Track Corrective Actions To Closure | Whenever there are deviations in the planned parameters (in metrics performances or nonconformance’s reported during process reviews), project manager identifies the corrective action and tracks it to closure |
| Project Manager | Update Plan | Project manager updates the plan and schedule periodically based on triggers eg. Triggers from project reviews, change requests, re-estimations, deviations. Project manager communicates the updated plan with the relevant stake holders (as applicable) |
| HOD | Conduct milestone review meeting | HOD periodically (as per review frequency defined in Org level PMP) review status of the project with PM and team members. Project manager prepares MOM and share with relevant stakeholders and track action items to closure. |
| SQA | Conduct Periodic Process Compliance Audit | SQA conducts process compliance audit on monthly basis. Refer internal audit procedure for details |

Exit Criteria:

- All deliverables are delivered

Verification and Validation:

- Process compliance audit by SQA

- Project progress review by PM as per review frequency defined in Org level PMP

Measurements:

- All planned parameters tracked

- Effort spent in project monitoring activities