Project Planning

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 4-Nov-14 |  | NA | Initial Version |
| 1.0 | SEPG | 26-Nov-14 |  | NA | Initial version |

Purpose:

The purpose of project planning process is to ensure project plan is defined to guide the execution of project

| Inputs | Outputs |
| --- | --- |
| - Project Initiation meeting minutes - All documents received from Presales stage - Historical data from Organizational Repository | - Baselined Project Management plan - Baselined Project Schedule - WBS in PMS tool |

Entry Criteria:

- Project Initiation Meeting conducted

- High level schedule available

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Project Manager | Prepare Project Level Project Management Plan (PMP) | Project manager uses project information report, documents received from sales team and user for creating project level project management plan (PMP) |
| Project Manager | Define Project Specific Processes | Project manager defines the project specific processes applying the tailoring guideline (where applicable) Project manager identifies and documents - Project methodology - Project category - Tailoring applied in the project - Project scope and deliverables - issues escalation mechanism - Roles and Responsibilities - plan for skill gap fulfillment - Training plan - project work environment - plan for stakeholder involvement - Issues with corrective & Preventive actions - Risk management - Lessons learnt & best practices |
| Project Manager | Refer Historical Data | Project manager refers historical process data base, organization repositories for estimation, preparation of Project level PMP. Project manager validate historical data for its appropriateness to the project. |
| Project Manager | Identify Risks | Project manager identifies project risks associated with the project and logs risk with mitigation and contingency plan in risk register. |
| Project Manager | Prepare Work Breakdown Structure | Project manager prepares Work Breakdown Structure (schedule plan) and evolves schedule. |
| Project Manager | Review PMP | Project manager initiates the review of PMP with relevant stakeholders. Reviewers review PMP and share review feedback in email or review report. In case there are review comments, project manager Incorporate review comments and shares with the reviewers for re-verification. Once all the review comments are closed, project manager seeks approval on PMP from HOD |
| Project Manager | Baseline PMP | Project manager baseline PMP and release it to relevant stakeholders (as applicable) Project manager discuss the content of the PMP with team members |
| Project Manager | Update The Project Management Plan | Project manager update the project management plan, if there is change in scope of the project, change in metrics goals, or change in project execution methodology |

Exit Criteria:

- Baseline project management plan

Verification and Validation:

- Review of PMP

Measurements:

- Effort spent in Project planning activity

- Schedule for project planning activity