## Working Revision History
Working Revision History
Version | Baseline Date | Change Description | Author | Reviewed By | Approved By
Name & Title

## Master-PMP
MASTER LEVEL PMP
Vertical Name
Vertical Head Name
Last updated
1. OVERVIEW of VERTICAL
2. PROJECT EXECUTION METHODOLOGY
There are various ‘Execution Methodologies’ used to execute the different types of projects viz small, medium, large etc. using difernet life cycle model vis Waterfall, Agile etc. <<Please explain the ‘Execution Methodology’ followed by the projects under taken.>>
3. TOOLS
Phase/Activity | Tools
Configuration Management
Test Planning
Unit testing
Automated Testing
Deployment
Defect Tracking
Design
Development
Project Management
Timesheet
Documentation
Code Review
Production Support
4. PROJECT IINTERNAL ESCALATION
Every project must follow an escalation matrix for timely resolution of issues. | The escalation matrix used by project is: <Tempate ID need to be provided>
5. PROJECT METRICS
Project should identify Metrics and KPIs to review project progress quantitatively. Metrics are defined for each project type at org level. For Eg: 1. Cost Metrics (Cost Variance from Plan) 2. Earned Value Measures 3. Time Metrics 4. Schedule Metrics 5. Scope Metrics 6. Quality Metrics (Defect Reports) 7. Risk & Issue Metrics | Add a list of metrics (Schedule and Quality) you are maintaining for this project.
6. PROJECT MONITORING AN CONTROL
Progress review type | Participant | Tracking Elements | Mode | Frequency / Event
Project Progress Review Meeting | Entire project team | User requirements, complaints &dependencies, | Face to face meeting | Weekly / Event driven
Status tracking – Plan Vs Actual (Effort, Schedule, Cost, Size)
Project Risk elements, Technical issues and queries,
Critical resources tracking,
Project support issues
Other issues & concerns
Review of earlier MOM
Senior Management Review Meeting | Senior Management, HOD, PM, Team member (as applicable) | Project progress review – Plan Vs Actual (Effort, Schedule, Cost, Size) | Face to face meeting | Monthly
Metrics performance review
Escalated project issues
User requirements, complaints & dependencies
Audit issues & Tailoring option review
Other issues & concerns
Review of earlier MOM
Milestone Review Meeting | HOD, PM, Team member (as applicable) | Project progress review – Plan Vs Actual (Effort, Schedule, Cost, Size) | Face to face meeting | Monthly/ Event driven
Metrics performance review
Escalated project issues
User requirements, complaints & dependencies
Audit issues & Tailoring option review
Other issues & concerns
Review of earlier MOM
7. ESTIMATION TECHNIQUE
Every project must estimate the size of the project. | All types of projects will use "COMPLEXITY POINT ESTIMATION TECHNIQUE" to estimate the size of the project.
8. AUDIT PLAN
Audit Type | Frequency | Audit item | Auditee (Specify the roles like PM etc.) | Release Audit Sampling Criteria
Release Audit | As and when the product/software is ready for release using Release Audit checklist | Release artifacts | Developer/TL/PM
CM audit | On monthly basis (using CM audit checklist) | CM process related work products | CM
Project Compliance Audit | Monthly | To verify the project execution activities | PM
9. CONFIGURATION MANAGEMENT PLAN
List of Cis/Managed Items | Naming Convention | Criteria for baselining | Location
CCB Composition
Change Reqquest Workflow
Configuration Audits
Backup and Restotation
Note on A19: The list below is just a suggestion, please feel free to add/delete a row as required
Note on A43: The list below is just a suggestion, please feel free to add/delete a row as required
Note on A77: The list below is just a suggestion, please feel free to add/delete a row as required

## Template Revision History
Revision History
Version | Baseline Date | Change Description | Author | Reviewed By | Approved By
Name & Title
V1.0 | 2021-11-26 | Initial Version