## Project Information
Project Information
Project Code
Project Name
Project Manager
Client Name
Updated By
Last Updated on

## Team Details
Team Details
S. No. | Name of Team Member | Role | Project Responsibilities | Contact Information | Date of Allocation | Date of Release | % Allocation | Status | Remarks
1 | ABC | Tester | Writing Test Cases, Execution of Test Cases | 4110 (extn) | 2014-01-12 | NA | 100 | Assigned

## Skill Matrix
Skill Matrix
S. No. | Skill Required | <Team Member A> |  | <Team Member B> |  | <Team Member C>
|  | Needed | Actual | Needed | Actual | Needed | Actual
1 | .Net | Hands on | Basic

## Training Plan
Training Plan
S.No | Training Topic | Mode of Training | Name of Resource | Training Required by Date | Name of Resource Attended the Training | Actual Training Completion Date | Effort Spent in Training | Status of Training
1 | .Net | Classroom | ABC | 2014-05-05 | ABC | 2014-05-05 | 8 hours | Completed

## Recruitment Plan
Recruitment Plan
S. No. | Required Skills | Desired Skills | No. of Resources | Needed on or Before | Actual Date of Hiring | No. of Resources Hired | Status | Remarks
1 | SQL | C# | 2 | 2014-06-01 | 2014-06-02 | 1 | In progress

## Engineering Tasks
Engineering Tasks
S.no | Phase | Activity | Performed By | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Effort Data |  |  | Schedule Data | [5 empty] | Status
|  |  |  | Planned Effort (Phrs) | Revised Effort (Phrs) | Actual Effort (Phrs) | Planned Start Date | Planned Completion Date | Revised Start Date | Revised Completion Date | Actual Start Date | Actual Completion Date

## Project Management Tasks
Project Management Tasks
S.No | Project Management Phase | Activity | Total | 6 | 9 | 12 | 2014-04-01 | 2014-05-10 | 2014-04-01 | 2014-05-10 | 2014-04-01 | 2014-05-12
|  |  | Task Owner | Effort Data |  |  | Schedule Data | [5 empty] | Status
|  |  |  | Planned Effort (Phrs) | Revised Effort (Phrs) | Actual Effort (Phrs) | Planned Start Date | Planned Completion Date | Revised Start Date | Revised Completion Date | Actual Start Date | Actual Completion Date
| Project Initiation Phase | <Prepare PIR> |  | 2 | 3 | 4 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | Closed
| Project Initiation Phase | <Project Initiation Meeting> |  | 2 | 3 | 4 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-12 | 2014-05-12 | Closed
| Project Initiation Phase | <Initiation Phase Review> |  | 2 | 3 | 4 | 2014-04-01 | 2014-04-01 | 2014-04-01 | 2014-04-01 | 2014-04-01 | 2014-04-01 | Closed
| Project Initiation Phase | <Training of Team>
| Project Initiation Phase | <Process Tailoring and Deviation>
| Project Initiation Phase | <Setting up of tools>
| Project Initiation Phase | <Providing Access Rights>
| Project Planning Phase | <PMP Preparation>
| Project Planning Phase | <PMP Review>
| Project Planning Phase | <Estimation>
| Project Planning Phase | <Planning Phase Review>
| Project Monitoring Phase | <Metrics Tracking and Analysis>
| Project Monitoring Phase | <Project Progress review Meeting>
| Project Monitoring Phase | <HOD Review Meeting>
| Project Monitoring Phase | <Risk Identification and Monitoring>
| Project Monitoring Phase | <SQA Review>
| Project Monitoring Phase | <Configuration Activities>
| Project Monitoring Phase | <Configuration Audit>
| Project Monitoring Phase | <Phase end reviews>
| Project Monitoring Phase | <Training of Team>
| Project Monitoring Phase | <Stakeholder Management>
| Project Monitoring Phase | <Estimation Revisit>
| Project Monitoring Phase | <Decision Analysis and Resolution>
| Project Closure Phase | <Prepare Project Closure Report>
| Project Closure Phase | <Project Closure Meeting>
| Project Closure Phase | <Project Closure Review>
| Project Closure Phase | <Organisation Repository Updation>
| Project Closure Phase | <Data Archiving>

## Phase Wise Tracking
Phase Wise Tracking
Project Size (CP) | 192
Phases | Total Effort Data |  |  | Schedule Data | [5 empty] | Defect Data |  |  |  | Cost |  |  | Status | Phase Wise Metrics
| Estimated effort (Phrs) | Revised Effort (Phrs) | Actual effort (Phrs) | Estimated Start date | Estimated Completion date | Revised Start date | Revised Completion date | Actual Start date | Actual Completion date | Internal Review Defect | External Review Defects | Internal Testing Defects | External Testing Defects | Estimated Cost | Revised Cost | Actual Cost |  | EVa (%) | EVb (%) | SVa (%) | SVb (%) | Cost Variance%
Requirement Development Phase | 0 | 0 | 0 | 2014-05-01 | 2014-05-10 | 2014-05-01 | 2014-05-10 | 2014-05-01 | 2014-05-10 | 10 |  |  |  | 1 | 1 | 1 | Closed | #DIV/0! | #DIV/0! | -14.2857 | -14.2857 | 0
Design Phase | 0 | 0 | 0 | [13 empty] | Not Started
Coding and Unit Testing Phase | 0 | 0 | 0 | [7 empty] | 3
Testing | 0 | 0 | 0
Acceptance Testing | 0 | 0 | 0 | [8 empty] | 5 | 3
Integration Testing | 0 | 0 | 0
Certification TestIng | 0 | 0 | 0
STQC | 0 | 0 | 0
Project Management | 6 | 9 | 12 | 2014-04-01 | 2014-05-10 | 2014-04-01 | 2014-05-10 | 2014-04-01 | 2014-05-12 | [7 empty] | Closed | 100 | 33.3333 | 0 | 0
Grand Total | 0 | 0 | 0 | 2014-04-01 | 2014-05-10 | 2014-04-01 | 2014-05-10 | 2014-04-01 | 2014-05-12 | 10 | 3 | 5 | 3 | 1 | 1 | 1 | Closed | #DIV/0! | #DIV/0! | 0 | 0 | 0
Formulas:
Schedule Data = MIN(E5:[Schedule Data, row above])
Estimated Completion date = MAX(F5:[Estimated Completion date, row above])
Revised Start date = MIN(G5:[Revised Start date, row above])
Revised Completion date = MAX(H5:[Revised Completion date, row above])
Actual Start date = MIN(I5:[Actual Start date, row above])
Actual Completion date = MAX(J5:[Actual Completion date, row above])

## Project Metrics Performance
Metrics Performance
Overall Metrics | Unit | LSL | Goal | USL | Current Value
Overall Effort Variation Initial (Eva) | % | -20 |  | 20 | #DIV/0!
Overall Effort Variation Baselined (Evb) | % | -20 |  | 20 | #DIV/0!
Overall Schedule Variation Initial (Sva) | % | -20 |  | 20 | 0
Overall Schedule Variation Baselined (SVb) | % | -20 |  | 20 | 0
Review Effectiveness (RE) | % | 55 |  | 75 | 66.6667
Testing Efficiency (TE) | % | 80 |  | 100 | 62.5
Defect Removal Efficiency (DRE) | % | 80 |  | 100 | 71.4286
Defect Density (DD) | Defects/CP | 0 |  | 5 | 0.10938
Productivity | CP/Hour | 0 |  | 5 | #DIV/0!
Median Time To Repar (MTTR) | Hours | 0 |  | 5 | 35
Reopen % | % | 0 |  | 5 | 0
Cost Variance | % | -20 |  | 20 | 0

## Support
Support
S. No. | Issue No. | Reported Date / Time | Incident Description | Category (A or B) | Priority | Raised By | User mail id | User Contact details | Receipt Mode | Actual Start Date / Time | Release End Date / Time | Hold time (hrs.) or Clarification time (hrs.) | Total Effort Spent (Hrs.) | Resolved By | Enhancement ID | Current Status | Time to Repair (TTR) (Hrs.)
| 1 | 2013-05-12 08:00 | [7 empty] | 2013-05-12 01:00 | 2013-05-13 19:00 | 0 |  |  |  | Closed | 35
Note on P2: Mention the enhancement or change request id
Note on R2: TTR is measured as the time taken from reporting date to actual end date.

## Risk Register
Risk Register
Date Identified | Risk Source | Phase Identified | Risk Category | Risk Title | Risk Description | Owner | Initial |  |  | Current |  |  | Mitigation Plan | Contingency Plan | Cost of Risk | Cost of Mitigation Plan | Cost Benefit Analysis | Escalation Threshold | Remarks | Update Date | Status
[7 empty] | Probability | Impact | Risk Priority - Initial | Probability | Impact | Risk Priority - Current
2014-05-01 | Past Experience | Requirement Development | Project Management | Complete knowledge of Application | Team members do not have the knowledge of all application | PM | High | High | High | Low | Low | Low | Regular cross training and knowledge transfer session would be planned from senior team members | Tasks will be assigned to SMEs | 10% overrun (100000 0*0.1 = 100000) | 5 hours of KT session weekly for all team members for one month (5 hours * 4 weeks * 500) | Cost of mitigation is less than the cost of risk. |  |  | 2015-05-01 | Didn’t Occur and Open

## Change Management
Change Management
Change Request No. | Date Received | Requested By | Priority | Severity | Assigned to | Change Request Status | Change Request Close Date | Remarks
1 | 2014-05-01 | User | High | Medium | Team Lead | Waiting for approval

## Issue Management
Issue Management
S. No | Issue Description | Raised By | Date Raised | Internal / External | Severity | Owner | Is the Issue Escalated | Escalated To | Current Status | Closed on | Issue is Recurring | Remarks
1 | Test Environment not available | Tester | 2014-05-05 | Internal | Medium | SSM | No | NA | Open |  | No

## Corrective & Preventive Action
Corrective and Preventive Action
Date | Issue / Variation | Cause for Variation | Corrective Action | Owner | Target Date of Completion | Actual Date of Completion | Status of Corrective Action | Remarks
2014-05-05 | Delay in completion of Requirement phase | SME not available | SME will be identified for requriement phase and other phases | SSM | 2014-05-15 |  | Open

## Lessons Learnt-Best Practices
Lessons Learnt - Best Practices
S.No. | Lessons Learnt/Best Practices | Benefit Realized

## Holiday List
Holiday List
2014-01-14
2014-01-26
2014-03-17
2014-04-08
2014-04-13
2014-05-14
2014-07-29
2014-08-15
2014-08-18
2014-10-02
2014-10-03
2014-10-06
2014-10-23
2014-11-04
2014-11-06
2014-12-25

## Revision History
Revision History
Ver. No. | Date | Prepared by/Modified by | Significant changes | Approved By