Requirement Development and Management Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 1-Oct-14 |  | NA | Initial Version |
| 1.0 | SEPG | 26-Nov-14 |  | NA | Initial version |
| 1.1 | SEPG | 25-Feb-19 |  | NA | - Added S.No. column - Added two new additional steps s.no. 5 and 6 which are already in practice but not added earlier |
| 1.2 | Prabhakar Jha | 8-Nov-21 | Manish Singla | NA | Added point no. 8 – “Final SRS walkthrough & Acceptance” |

Purpose:

Purpose of the requirement development process is to detail out the requirements to establish common understanding of requirements between user/stakeholder and the project team and manage the changes in the requirement.

| Inputs | Outputs |
| --- | --- |
| - Approved Technical Proposal - Terms of Reference document (if applicable) | - Approved Software Requirement Specification (SRS) - Query log - Updated Requirement Traceability Matrix (RTM) |

Entry Criteria:

- User approved Technical Proposal

- Terms of Reference document (if applicable)

- Project Kick-off Meeting conducted (MOM)

Steps:

| S.No. | Responsibility | Action | Description |
| --- | --- | --- | --- |
|  | Project Manager | Analyse Technical Proposal | Project Manager along with the SME (Business Analyst/Functional Consultant) studies the Technical Proposal document. |
|  | Business Analyst/ PM | Prepare Questionnaire | Prepare the questionnaire to list down all the requirements that will help in requirement gathering. |
|  | Business Analyst/ PM | Gather Requirements | Initializes the collection of explicit (AS-IS, TO-BE), implicit and nonfunctional requirements from customer/user representative. Information can be captured through questionnaires. Other mechanism for gathering requirements may be interviews, facilitated workshops and observations. |
|  | Business Analyst/ PM | Raise Queries | If there are queries, project team can raise the queries with the customer using query log. |
|  | UI Developer | Homepage Design | UI developer creates the homepage design layouts for review by customer. There would be more than one design layouts for selection based on the customer recommended websites/web applications/ mobile app. |
|  | Business Analyst/ PM | Approval on homepage | PM/BA sends the designed homepage layouts to customer for selection and approval. If customer suggests some modification in the selected design, then PM/BA sends it back to the UI developer for updation. The modified selected design layout is then reviewed and approved by customer. This activity runs in-parallel with SRS creation. |
|  | Business Analyst/ PM | Prepare SRS | Business Analyst or PM prepares the Software Requirement Specification (SRS) based on the requirement understandings. |
|  | Implementation/Development Team (Project Team) | Final SRS walkthrough & Acceptance | PM/BA to plan and execute final SRS walkthrough with Implementation / development team for the feasibility of requirements before taking approval from client. |
|  | Project Manager/ HOD | Review SRS | PM or HOD reviews the SRS document using the SRS review checklist. PM/BA record the review comments in the review report. Business Analyst/PM update the SRS based on the review comments and submits back for re- verification. |
|  | Project Manager / Business Analyst | Artifacts related to SRS (Wireframes, etc.) | Capture all the wireframes in the SRS document in the designated section. |
|  | Business Analyst | Prepare Requirement Traceability Matrix | Business Analyst/Functional Consultant prepares the requirement traceability matrix (RTM). |
|  | User | Approve SRS | Business Analyst/PM seeks approval from user representative on the SRS. |
|  | Project Manager | Baseline SRS | PM will baseline the SRS and put under version control |
|  | Business Analyst/PM | Communicate Requirements | Business Analyst or PM shall communicate the accepted requirements to project team and take their commitments. |
|  | Business Analyst/ PM | Manage Changes To Requirements | Manage changes to the requirements throughout the project life cycle, using the change control procedure. |

Exit Criteria:

- Approved Software Requirement Specification (SRS)

- Review report updated with all review comments tracked to closure.

Verification and Validation:

- SRS Signoff by user

Measurements:

- Schedule for requirement development procedure

- Effort spent on requirement development procedure