Risk Management

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 4-Nov-14 |  | NA | Initial Version |

Purpose:

Purpose of risk management process is to ensure risks are identified, analyzed and mitigated in the project

| Inputs | Outputs |
| --- | --- |
| - Project Management Plan - Request for Proposal - Purchase Order | - Risk management sheet in PMWB - Risk updated in project closure report - Risk updated in organizational Risk Database |

Entry Criteria:

- Project is assigned to Uneecops

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Project Manager | Identify Risks | Project manager will identify project risk based on - Study of request for proposal or purchase order - QMS risk database - Monitoring project milestones & performance - Environmental changes - Stakeholder changes and expectations - Past incidents in the projects - Any other Project manager can seek inputs from stakeholders during risk identification |
| Project Manager | Assess Risk Impact | Project manager will analysis the impact of risks (E.g impacts on cost, schedule, scope or quality of deliverable). |
| Project Manager | Estimate the probability of occurrence for each risk | Project manager will assess the likelihood of occurrence of the risk or probability of occurrence of risks. |
| Project Manager | Prioritize the risk based on risk index | Based on the product of risk impact and probability of occurrence of risk, project manager will derive the priority of the risk |
| Project Manager | Identify risk response strategy | Based on the risk prioritization, project manager will identify and prepare mitigation plan or contingency plan (as applicable). Also, project manager will assess cost of risk, cost of mitigation and perform cost benefit analysis |
| Project Manager | Implement mitigation plan | Project manager will implement the mitigation plan as identified in PMWB, to reduce the impact and probability of occurrence of risk |
| Project Manager | Implement contingency plan | Project manager will implement contingency plan in case project risk has occurred |
| Project Manager | Monitor the identified risks | Project manager will monitor the status of risk which are identified in the project and shall re-visit the impact and probability of occurrence of risk. If the current or revised status of risk is beyond the escalation threshold, project manager shall escalate the risk to the next level or user or relevant stakeholders. |
| Project Manager | Review the status of project risks | Project manager shall review the status of project risks project progress review meeting Also, HOD will review the status of project risks during senior management review meetings |
| Project Manager | Update organizational risk database | At the tie of phase end or project closure, project manager will specify the summary and status of risk occurrences in project closure report and update in organizational risk database |

Exit Criteria:

- Project is closed

Verification and Validation:

- Review of risks in Project progress review and reviews with HOD and other stakeholders.

Measurements:

- Risk Priority

Guideline

# Risk Identification.	Risk identification will be done based on source/triggers, which include

- Risk identified during study of initial requirement document

- Risks identified from QMS risk database

- Monitoring project milestones & performance

- Environmental changes

- Stakeholder changes and expectations

- Past incidents in the projects

- Other internal factors

- Other external factors

Risk will be classified under following categories

- Technology

- Environment

- Customer

- People

- Tools (H/W,S/W)

- Project Management

# Risk Analysis.	Risk analysis will be done in PMWB, to find out the probability and impact of the risk

- Impact Analysis will be done on cost/effort, schedule, quality and scope.

The rating will be given as High, Medium, Low based on the severity of the impacts

| Impact | Description |
| --- | --- |
| High | Failure cause a high degree of customer/organization’s top management dissatisfaction or Quality issues unacceptable to the user and it will result in major operational limitation till resolved, and no workaround is available or > 10 % schedule, cost/effort increase or |
| Medium | Failure would create a minor nuisance but the customer/organization can overcome it without performance loss < 10% schedule, cost/effort increase |
| Low | Failure would not be noticeable and would not affect the customer/organization’s process or product or Insignificant schedule slippage, cost/effort increase |

Cost would include human effort or infrastructure cost.

While performing the risk impact analysis, impact ratings can be scaled up based on the risk appetite of the project, but Impact rating cannot be scaled down

- Probability of Occurrence.	Probability rating of the risk will be determined (in PMWB) based on the probability of occurrence, using the following table:

| Probability Rating | Probability of Occurrence |
| --- | --- |
| High | Repeated failures or Failure is almost inevitable |
| Medium | Occasional failures |
| Low | Failure is unlikely to happen |

# Risk Prioritization.	Probability rating and impact obtained from risk analysis will be used for arriving at priority of risk, using the following matrix:

Risk Priority = Impact * Probability of occurrence

| Impact | Probability |  |  |
| --- | --- | --- | --- |
|  | Low | Medium | High |
| Low | Low | Low | Medium |
| Medium | Low | Medium | High |
| High | Medium | High | High |

# Risk Response Planning.	Based on the priority of risk, response panning will be done using the following table:

| RISK PRIORITIZATION | EXTENT OF PLANNING |
| --- | --- |
| Low | No explicit mitigation plan will be identified No explicit contingency plan will be identified Risk may be accepted as and when encountered |
| Medium | No explicit mitigation plan will be identified Contingency plan will be proposed |
| High | Mitigation plan will be mandatory Contingency Plan will be mandatory |

# Risk Mitigation and Contingency Plan.

- Risk Mitigation plan 	is the preventive action taken to reduce the risk probability, impact or both. The risk mitigation plan for a given risk includes methods used to avoid, reduce, and control the probability of occurrence of the risk

- Risk Contingency Plan 	is the corrective action which is required to deal with risk once it occurs.

# Cost Benefit Analysis.	Every risk for which a mitigation plan is identified, the following will be determined:-

- Cost of the risk (if encountered and not mitigated)

- Cost of the envisaged mitigation plan

- The cost benefit ratio as:

Cost of the risk (if encountered and not mitigated)

Cost of the envisaged mitigation plan

If the cost benefit ratio is less than 1, a prudent decision will be made about investing in the mitigation plan