Risk and Opportunity Management

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | PEG | 4-Nov-2014 |  | NA | Initial Version |
| 1.0 | SEPG | 01-Jul-2021 | SEPG Head | NA | - Modified the document to add opportunity related details as advised by external auditor from KPMG. Modification is required to comply with CMMi Dev 2.0 practices. - Added the details for Initial Opportunity Assessment and Opportunity Pursuit Plan and Risk related text in opportunity analysis and opportunity action planning sections. |

Purpose:

Purpose of risk and opportunity process is to ensure positive and negative risks are identified, analyzed and mitigated or implemented in the project.

| Inputs | Outputs |
| --- | --- |
| - Project Management Plan - Request for Proposal - Purchase Order - Risk database | - Risk Register - Opportunity tracker - Risks updated in project closure report - Risks updated in organizational Risk Database |

Entry Criteria:

- Project is assigned to Uneecops

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Project Manager | Identify Risks & opportunities | Project manager will identify project risks & opportunities based on - Study of request for proposal or purchase order - QMS risk database - Monitoring project milestones & performance - Environmental changes - Stakeholder changes and expectations - Past incidents in the projects - Any other Project manager can seek inputs from stakeholders during risk and opportunity identification |
| Project Manager | Assess Risk Impact | Project manager will analyze the impact of risks & opportunities (E.g impacts on cost, schedule, scope or quality of deliverable). |
| Project Manager | Estimate the probability of occurrence for each risk | Project manager will assess the likelihood of occurrence of the risks or probability of occurrence of identified risks |
| Project Manager | Prioritize the risks & opportunities based on risk index | Based on the product of risk impact and probability of occurrence of risk, project manager will derive the priority of the risks |
| Project Manager | Identify risk response strategy | Based on the risks prioritization, project manager will identify and prepare mitigation plan or contingency plan (as applicable). Also, project manager will assess cost of risk, cost of mitigation and perform cost benefit analysis For opportunities, PM can take actions for exploring and implementing the opportunities based on the guidelines |
| Project Manager | Implement mitigation plan | Project manager will implement the mitigation plan as identified in PMWB, to reduce the impact and probability of occurrence of risk. PM to implement action to maximize the opportunity. |
| Project Manager | Implement contingency plan | Project manager will implement contingency plan in case project risk has occurred |
| Project Manager | Monitor the identified risks | Project manager will monitor the status of risks which are identified in the project and shall re-visit the impact and probability of occurrence of risks. If the current or revised status of risk is beyond the escalation threshold, project manager shall escalate the risk to the next level or user or relevant stakeholders. |
| Project Manager | Review the status of project risks & opportunities | Project manager shall review the status of project risks in project progress review meeting Also, HOD will review the status of project risks during senior management review meetings |
| Project Manager | Update organizational risk database | At the time of phase end or project closure, project manager will specify the summary and status of risk occurrences in project closure report and update in organizational risk database |

Exit Criteria:

- Project is closed

Verification and Validation:

- Review of risks in Project progress review and reviews with HOD and other stakeholders.

Measurements:

- Risk Priority

Guideline

# Risk Identification.	Risk & opportunities identification will be done based on source/triggers, which include

- Risk identified during study of initial requirement document

- Risks identified from QMS risk database

- Monitoring project milestones & performance

- Environmental changes

- Stakeholder changes and expectations

- Past incidents in the projects

- Other internal factors

- Other external factors

Risk will be classified under following categories

- Technology

- Environment

- Customer

- People

- Tools (H/W,S/W)

- Project Management

# Risk Analysis.	Risk analysis will be done in PMWB, to find out the probability and impact of the risk

- Impact Analysis will be done on cost/effort, schedule, quality and scope.

The rating will be given as High, Medium, Low based on the severity of the impacts

| Impact | Description |
| --- | --- |
| High | Failure cause a high degree of customer/organization’s top management dissatisfaction or Quality issues unacceptable to the user and it will result in major operational limitation till resolved, and no workaround is available or > 10 % schedule, cost/effort increase or |
| Medium | Failure would create a minor nuisance but the customer/organization can overcome it without performance loss < 10% schedule, cost/effort increase |
| Low | Failure would not be noticeable and would not affect the customer/organization’s process or product or Insignificant schedule slippage, cost/effort increase |

Cost would include human effort or infrastructure cost.

While performing the risk impact analysis, impact ratings can be scaled up based on the risk appetite of the project, but Impact rating cannot be scaled down

- Probability of Occurrence.	Probability rating of the risk will be determined (in PMWB) based on the probability of occurrence, using the following table:

| Probability Rating | Probability of Occurrence |
| --- | --- |
| High | Repeated failures or Failure is almost inevitable |
| Medium | Occasional failures |
| Low | Failure is unlikely to happen |

# Risk Prioritization.	Probability rating and impact obtained from risk analysis will be used for arriving at priority of risk, using the following matrix:

Risk Priority = Impact * Probability of occurrence

| Impact | Probability |  |  |
| --- | --- | --- | --- |
|  | Low | Medium | High |
| Low | Low | Low | Medium |
| Medium | Low | Medium | High |
| High | Medium | High | High |

# Risk Response Planning.	Based on the priority of risk, response planning will be done using the following table:

| RISK PRIORITIZATION | EXTENT OF PLANNING |
| --- | --- |
| Low | No explicit mitigation plan will be identified No explicit contingency plan will be identified Risk may be accepted as and when encountered |
| Medium | No explicit mitigation plan will be identified Contingency plan will be proposed |
| High | Mitigation plan will be mandatory Contingency Plan will be mandatory |

# Risk Mitigation and Contingency Plan

- Risk Mitigation plan 	is the preventive action taken to reduce the risk probability, impact or both. The risk mitigation plan for a given risk includes methods used to avoid, reduce, and control the probability of occurrence of the risk.

- Risk Contingency Plan 	is the corrective action which is required to deal with risk once it occurs.

# Opportunity Management

# OPPORTUNITY CATEGORIZATION

| Business or revenue generation or cost reduction | Process efficiency | Quality of deliverable | People related | Technical solution | Better project governance or meeting project KPIs |
| --- | --- | --- | --- | --- | --- |
| Due to technology change, there may be more business opportunities | opportunity to improve process efficiency by removing non-value-added activities and thereby increasing the productivity | opportunity to increase the quality of product by introducing tools for review or increasing the skills of the resources | opportunity to up-skill the people on new technology or domain | Opportunity to make the architecture more scalable | Opportunity for better project governance or resource management like introduction of tools for project management |
| Due to regulatory or policy changes, more business opportunity |  |  |  |  |  |

# OPPORTUNITY DESCRIPTION

An opportunity description statement should describe opportunities that could positively affect work and plans. The first part of the opportunity statement should describe the positive impact and other half should describe the potential benefits for the same.

# Opportunity Analysis

Opportunity analysis (and prioritization) is the second step in the Risk and opportunity Management process. The goal of the risk and opportunity analysis step is to prioritize the items on the risk and opportunity list and determine which of these risks and opportunities warrant commitment of resources for planning. Risk and opportunity analysis involves conversion of risk data into a form that facilitates decision-making and opportunity data into a form that helps leveraging opportunities. Risk and opportunity prioritization ensures that the team members address the most important project risks and opportunities first. During this step, the team examines the list of risk and opportunities produced in the risk and opportunity identification step and prioritizes them for action.

# Initial Opportunity Assessment

The initial opportunity assessment is done with opportunity   assessment paraments   Probability, Impact, and opportunity factor. The opportunity factor is calculated using the formula Probability *Impact. Also expected benefit from opportunity and the expected cost to carry out the opportunity plan are also considered to take a decision on implementation of identified opportunity.

Impact:  This will be selected on scale of 1 to 10. For High impact Rating will be 10, Medium impact will be rated 5 and low impacted will be rated less than 5.

Probability:  Rating will be given as 30% to 70% for medium, more than 70% rating for high probability and less than 30% rating for low probability.

# Opportunity Pursuit

Decision on purse plan: The threshold to trigger an action will be decided based on outcome of probability multiplied by impact. The opportunity with high probability and impact are selected on a priority basis for implementation of opportunity action plans. Also, an opportunity value can be considered by subtracting expected cost from expected return while taking a decision to implement action plan.

# Strategies for Opportunities Handling

#### Exploit Add work or change the project to make sure the opportunity occurs

#### SHARE: Allocate ownership of opportunity to a third-party

# Opportunity Action Planning

Opportunity action planning involves benefits of opportunity by expecting the benefits and cost of opportunity which opportunity needs to be pursued. Opportunity Action plans are necessary for all opportunities. They address what to do further and maximize the impact.

Risk associated with action plans:  Also investigate on any risk associated to carry out the action plan and prepare a mitigation and contingency plan for identified risk in Risk and opportunity Register

# Cost Benefit Analysis

# Every risk for which a mitigation plan is identified, the following will be determined:-

- Cost of the risk (if encountered and not mitigated)

- Cost of the envisaged mitigation plan

- The cost benefit ratio as:

Cost of the risk (if encountered and not mitigated)

Cost of the envisaged mitigation plan

If the cost benefit ratio is less than 1, a prudent decision will be made about investing in the mitigation plan