Subcontract Management

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 11-Nov-14 |  | NA | Initial Version |

Purpose:

The purpose is to define the process of procurement, evaluation of vendors (technically and commercially), and to monitor the supply of product or services with respect to the qualitative requirements.

| Inputs | Outputs |
| --- | --- |
| - Approved Request for Proposal | - Statement of Work between Uneecops and Vendor - DAR form - Updated Vendor Performance Data |

Entry Criteria:

- Need identification for subcontract

- Senior management’s approval for outsourcing the defined tasks or project.

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| - Selection of Subcontractor |  |  |
| Project Manager | Prepare Business case | Project manager identifies the need for subcontracting the project work to the external vendor and identifies the qualitative requirements for subcontracting. Project manager prepares request for proposal and takes approval from HOD and senior management. If required, project manager may seek approval from customer |
| Project Manager | Invite Subcontractors | Project manager identifies the vendors or subcontractors and explains the statement of work or user requirement specification. The prospective subcontractors are normally selected based on the skill sets required for the execution of the project. Project manager publishes the request for proposal to the vendors |
| Project Manager | Review of proposal & selection of subcontractor | Vendors respond to the request for proposal. Project manager evaluates the technical and financial capability of the vendors based on the response submitted by the vendors. Criteria for evaluation or shortlisting could include - vendor’s prior performance records on similar work (if available) - vendors prior experience in similar applications, Vendors staff and resources available for performing the work, - Cost - Geographical location - Infrastructure facilities - Training facilities - Ramp up capability - Project management - Software engineering capabilities - Proposed delivery date of the product / site. Project manager can use formal evaluation procedure for evaluation of vendors. Project manager selects the vendors based on the evaluation |
| Project Manager | Award the Contract | Upon evaluation, project manager awards the contract for project work to the subcontractor or vendor. The contract or statement of work is agreed with Uneecops and vendor both. If required, project manager can seek approval from user. Note: The schedule mentioned in the contract to subcontractor should be in line with the overall plan of the project, where a part of work is subcontracted. |
| - Subcontract Management |  |  |
| Project Manager | Monitor the Progress | Subcontractor shall prepare a project plan (work breakdown structure) and it will be reviewed and approved by project manager. Project manager will track progress of work awarded to subcontractor on periodic basis. The frequency of monitoring should be at least monthly and actual status against planned activities, milestones, financials, new/changed issues, risks and any change to scope should be reported. |
| Configuration Controller | Manage Configuration | The configuration controller of the project shall monitor the configuration Management activities (Identification of CIs, Change Control, Version control and Configuration Status Accounting) of the subcontractor according to the configuration management process or as defined in the project management plan |
| SQA Team | Manage Process Quality | SQA team will carry out product audits of subcontracted work, monitor the subcontractor’s quality assurance activities at periodic intervals and report the results as defined in the project plan |
| Project Manager | Evaluate the Supplied Product | Project manager shall ensure the product supplied by the subcontractor is tested well before the acceptance of the product from subcontractor This testing is to test whether the software supplied by the subcontractor meets the requirements as agreed for the subcontracted portion of the project (the subcontracted portion may or may not include the complete project functionality). This testing is conducted according to terms and conditions written in the Contract. Test results are documented and action plan is agreed with the subcontractor for any test that fails to pass the UAT. Upon testing, project manager will provide sign off to the subcontractor. |

Exit Criteria:

- Product or service is procured

- The UAT is completed successfully

Verification and Validation:

- Review of progress of subcontractor periodically

- Test of the supplied product

Measurements:

- Schedule for subcontracted work

- Effort for subcontracted work

- Defects in subcontracted work