## Template Revision History
Revision History
Version | Baseline Date | Change Description | Author | Reviewed By | Approved By
Name & Title

## Test Log
Test Log
Project Name |  | OUMS | Project Code
Module Name |  |  | Module Version
Test Cycle No. |  |  | Test Execution Date
S. No. | Test Case ID | Executed By | Defect Description | Severity | Validity of Defect | Defect Type | Defect Cause | Phase Injected | Resolution | Resolved by | Resolved Date | Verified by | Verified Date | Status | Remarks
1 | GBT_03 | Shubham Singh | Input size and pattern for each value should be define in manner | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
2 | CM_19 | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
3 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
4 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
5 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
6 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
7 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
8 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
9 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
10 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
11 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
12 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
13 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
14 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
15 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
16 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
17 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
18 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
19 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
20 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
21 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
22 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
23 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
24 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
25 |  | Shubham Singh | system should flash alert mentioning the field name if user enter duplicate value(s) | Minor | Valid | UI Related defect | Frequent Requirement Change | Coding and Unit Testing Phase | Input text field and pattern validation was implemented as per PM suggestion | Rahul Patel | <Mention the date for defect resolution in DD-MM-YY format> | Priya Chauhan | <Mention the date for defect verification in DD-MM-YY format> | Closed
Note on E6: Mention the severity of the defect. Refer to Guidelines worsheet for details
Note on F6: Mention the validity of the defect
Note on G6: Mention the type of the defect. Refer the guidelines worksheet
Note on H6: Mention the cause of the defect. Refer the guidelines worksheet
Note on I6: Mention the phase in which defect was injected or introduced

## Setup (hidden)
Defect Type | Defect Cause | Phase Injected
Missing or Incomplete Requirements | Delayed Clarification | Requirement Development Phase
Incomplete or incorrect test data | Frequent Requirement Change | Design Phase
Code not Modular | Improper Communication | Coding and Unit Testing Phase
UI Related defect | Inadequate Process | System and Integration Testing Phase
Deviation from Coding Standards | Inadequate Review | Acceptance Testing Phase
Logical Flow/Sequencing defect | Inadequate Skill Level
Grammatical or Spelling mistake or Formatting defect | Inadequate Training / Education/ Awareness
Deviation from Standard Template | Insufficient Testing
Section not filled
Any Other

## Guidelines
Defect Severity |  |  | Defect Type |  |  | Defect Cause
S. No | Severity | Description | S. No | Defect Type | Description | S. No. | Defect Cause | Defect Cause Description
(i) | Major Defect | is one that is likely to create failure of the unit for its intended purpose. | (i) | Missing or Incomplete Requirements | Requirements are missed out in the requirements document or additional inputs are required for the requirements to complete the requirement document. This defect type is applicable in requirement phase | (i) | Delayed Clarification | There can be scenarios wherein the clarifications required for urgent requests or requirements are received beyond the target date.
(ii) | Minor Defect. | is a discrepancy from the standards, but one that is not likely to affect the usability of an object. | (ii) | Code not Modular | Code not organized properly and number of lines in the functions is more than as specified in coding guidelines. This defect type is applicable in coding phase | (ii) | Frequent Requirement Change | . Frequent change in requirement led to this defect.
|  |  | (iii) | UI Related Defect | User interface related defect resulting due to improper implementation of the UI design. This defect type is applicable in coding phase | (iii) | Improper Communication | Misunderstanding what was wanted. Either you misread the design document or did not understand the requirements.
|  |  | (iv) | Deviation from Coding Standards | Non adherence to coding guidelines defined/followed in project. This defect type is applicable in coding phase | (iv) | Inadequate Process | A fault in your process led you to do the wrong thing
|  |  | (v) | Logical Flow/Sequencing defect | The logical flow mentioned in the code not in correct sequence and not as per logic defined in the design document. This defect type is applicable in coding phase | (v) | Inadequate Review | So it is a simple case of oversight or goof.
|  |  | (vi) | Grammatical or Spelling mistake or Formatting Defect | Spelling / grammar mistakes and other editorial errors in the code / documents or Formatting of code / content in documents is not correct / complete. This defect type is applicable in all the phase | (vi) | Inadequate Skill Level | Project teams not skilled to execute the projects based on Specific technology / Domain
|  |  | (vii) | Deviation from Standard Template | Deviation from QMS standard template. If tailoring approval is sought for using the project specific template, the template being used and template for which deviation is approved are not matching. This defect type is applicable in all the phase | (vii) | Inadequate Training / Education/ Awareness | Inadequacies have occurred due to education, training, lack of domain knowledge etc.
|  |  | (viii) | Section not Filled | All sections not completely filled. This defect type is applicable in all the phase | (viii) | Insufficient Testing | Testing not adequate done for the project to satisfy the project requirements
|  |  | (ix) | Incomplete or Incorrect Test Data | Test data created for testing is not complete or is not correct
|  |  | (x) | Any Other | Any other Type of defects