Change Control

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 28-Oct-14 |  | NA | Initial Version |

Purpose:

Purpose of the change control procedure is to identify the change request, analyse the impact of change request, track change request till closure, throughout the life cycle of project.

| Inputs | Outputs |
| --- | --- |
| - Change request received | - Filled Change Request Form - Filled Impact Analysis Form - Updated PMS tool & Project level PMP (whatever applicable) - Updated Requirement Traceability Matrix |

Entry Criteria:

- Change Request is received

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Team Lead or Project Manager | Receive Change Request | Team Lead/PM receives change request (CR) from user or internal team members in change request form or email. |
| Change Control Board (CCB) | Analyze Change Request | Change Control board performs analyses the impact of change request for: - Items or functionality affected by the proposed change - Efforts involved - Effect on Delivery Schedule - Priority of change |
| Change Control Board | Communicate Changes | Change Control Board communicate and negotiate changes with the relevant stakeholders. Also, CCB identifies the risks related to implementation of change request |
| Change Control Board | Accept or Reject Change Request | Based on the impact analysis and negotiation with the stakeholders, CCB decides whether to approve or reject the change request. In case the change request is rejected, CCB send the notification to the stakeholder and closes the change request In case Change Request is approved, CCB notify the team member to execute the change(s). |
| Configuration Controller | Hand Over Configuration Items(s) | - Hand over the item(s) to the team as per Change Request Form for implementation |
| Team | Implement Change Request | - Development and testing team: - Implements necessary changes to the relevant product/product documentation - Perform reviews and tests to ensure that changes have not caused any unintended effects on the already tested and released baseline - Update Traceability Matrix for the changes - Seek signoff from the customer/end user |
| Configuration Controller | Track Status of Change Request | - CC updates configuration status report for new released item (s) and update the baselines. - CC updates PMS & Project Level PMP (whatever Applicable) for status of change requests and track the change request till closure |

Exit Criteria:

- Change request is closed

Verification and Validation:

- Review of change request form and impact analysis documents

Measurements:

- Number of changes accepted and implemented