Configuration Management

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 28-Oct-14 |  | NA | Initial Version |

Purpose:

Purpose of the configuration management procedure is to identify items for configuration, to manage baseline, to monitor status of configuration items and to perform configuration management audits throughout the life cycle of project.

| Inputs | Outputs |
| --- | --- |
| - Reviewed artifact | - Baseline Configuration Management Plan - Baseline artifacts - Backup taken - Filled Configuration Audit Checklist |

Entry Criteria:

- Project Kick off meeting conducted

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| - Configuration Management Planning |  |  |
| Project Manager | Identify configuration Controller | Project Manager identifies configuration controller (CC) for performing configuration management activities in the project. Ideally, tech lead should perform the part time responsibility of configuration controller. |
| Project Manager | Prepare Configuration Management Plan | Project Manager along with configuration controller prepares configuration management plan (as a part of PMP). Configuration management plan shall include: - Identification of project configuration items - Classification of software documentation as configuration items or managed Items. - Identification of directory structure, its contents, with appropriate access control mechanism - Identification of naming convention and labeling mechanism. - Identification of members of Change Control Board (CCB) for the project. - Plan for configuration management audits - Identification the CM tool to be used in the project. Project manager can apply formal evaluation procedure while selection of Configuration management tool (if applicable) |
| - Configuration Management Execution |  |  |
| Configuration Controller | Set up Environment | As per the Configuration management plan, configuration controller sets up the configuration environment. This includes: - Creation of project folder/directory structures as planned - Setting up the configuration management tool (if any). - Provide access rights to team members (as applicable) |
| Configuration Controller | Maintain configuration items in the CM repository. | CC allocates version number to each Item on its completion or release (for the first time or after a change) CC maintains all the configuration items in the CM repository. |
| Configuration Controller | Communicate To Project Team | CC Communicate the new version of the software documentation and the changes to the stakeholders as documented. |
| Configuration Controller | Take Backup and Restore | Configuration controller ensures that periodic backup of the data pertaining to configuration items if taken (as per organizational procedure). CC restores the backup files once in a quarter to ensure backup is restorable. |
| - Configuration Audits |  |  |
| Peer Configuration Controller | Conduct Configuration Management Audit | Based on the configuration audit plan in PMP, peer configuration controller (from other project) conducts Configuration audits using configuration audit checklist to ascertain that configuration management is being carried out. PM/TL ensures closure of reported issues. |

Exit Criteria:

- All finding from configuration management audit are closed

- Project is closed

Verification and Validation:

- Review of configuration management procedure using configuration audit checklist

Measurements:

- Effort spent on configuration management activities

Guideline

# Configuration Identification.

- Configuration Item (CI).

- Any artifact that is subject to the formal change management and version control procedure is considered configuration item. These are also termed as Baseline Items.

- Configuration items can include hardware, equipment and tangible assets as well as software and documentation. Example of artifact that may be part of a configuration item include the following:-

- Project Management Plan

- Contract or Purchase Order or Work order document

- Estimates

- Project Schedule

- Statement of Work or Technical Proposal

- Software Requirement Specification

- Technical Design Document

- Test Plan

- Test Cases

- Source code

- User Manual

(iii) Criteria of baseline can be the completion of formal review and acceptance of the work product.

(iv) Criteria for revision of baseline can be internal or external change request.

- Managed Item.	Any artifact that is not designated as a configuration item is considered as a managed item.

- MOM

- Org Level PMP and PROJECT LEVEL PMP

- Checklists

- Requirement Traceability Matrix

# Labeling and Numbering of Configuration Items.

# (a)	Every version-able artifact shall have revision history indicating the revision number and nature of changes in every release.

(b)	All project documents will use following version numbering convension-

- All draft versions of documents will start as 0.1. Next draft version after modification will be 0.2 and so on till approval.

- After document gets approved, it will be baselined as version 1.0

- Subsequent version after approval will be incremented by 0.1 i.e. version 1.1 i.e. minor changes baseline

- All major changes baseline should have versioning as 2.0, 3.0 ......

# Naming Convention

# Every artifact generated by the project will have a unique name

# Following format will be used to name various document created under this project.

# Projectname website - <CI Name>.<file extenstion>   or  Projectname webapplication - <CI Name>.<file extenstion>

# For example, risk register of project will be named as below using above format-

# GSDS  website - Risk Register.xls   or   APMS Webapplication - Risk Register.xls

# Following format will be used to name customer status reports created under this project.

# Projectname  website - Project Status Report_<ReportDate>.<file extenstion>

# For example, status report of project will be named as below using above format-

# GSDS  website - Project Status Report_05Jun18.pdf

# Change Control Board

(a)	Change Control Board comprises of CCB Chairman (HOD or PM), Configuration controller, Technical lead, team members depending upon nature of the change request.

(b)	At least two members should be part of CCB at any point of time.

(c)	User representative’s involvement in approval of change request will be necessary only when the change has an impact on cost, schedule, requirement, scope and quality.

(d)	CCB will review, analyze and approve the CRs based on the following parameters:-

(i)	Affected products / components

- Impact on effort / schedule / cost to implement change

- Impact on existing functionality

(iv)	Assessment of associated risks due to the proposed change

(e)	CCB ensures that all required documentation and related plan have been updated and put under version control.

# Configuration Status Accounting.

(a)	Configuration status accounting is an element of Configuration Management, consisting of the recording and reporting of information needed to manage a configuration effectively.

(b)	Configuration status accounting keeps track of the following:-

(i)	Status of configuration items.

    - Status of change requests.

(c)	Status of change requests are tracked through change management sheet in PMS TOOL & PROJECT LEVEL PMP (WHATEVER APPLICABLE).