## Project Plan
Agile Web Application WBS - PMS Project Template
Project Group | Project Name | Milestone | Task | Type | Task Owner | Start Date | End Date
eGov |  | Project Initiation | Project handover meeting with HOD | Task
eGov |  | Project Initiation | Project Kick-off meeting (Internal) with project team members | Task
eGov |  | Project Initiation | Project Kick-off presentation (External) creation & finalisation | Task
eGov |  | Project Initiation | Project Kick-off meeting with customer | Task
eGov |  | Project Initiation | Project schedule plan creation in PMS tool | Task
eGov |  | Requirements Gathering & Analysis | Requirements analysis and SRS documentation | Task
eGov |  | Requirements Gathering & Analysis | Home page design layouts creation | Task
eGov |  | Requirements Gathering & Analysis | Home page design approval by customer | Task
eGov |  | Requirements Gathering & Analysis | Final workflow walkthrough & validation with customer | Task
eGov |  | Requirements Gathering & Analysis | SRS review & finalisation (Internal) | Task
eGov |  | Requirements Gathering & Analysis | SRS approval & Sign-off by customer | Task
eGov |  | Requirements Gathering & Analysis | Requirements Traceability Matrix (RTM) creation & update till requirements phase | Task
eGov |  | Requirements Gathering & Analysis | WBS tasks creation and resources assignment in PMS/Agile PM tool for complete development | Task
eGov |  | Sprint Zero | Create Product backlog, Epics and User Stories | Task
eGov |  | Sprint Zero | Create release plan | Task
eGov |  | Sprint Zero | Create Technical Design Document (TDD) | Task
eGov |  | Sprint Zero | Scrum team formation and defining team space | Task
eGov |  | Sprint Zero | Prepare development and build environment (development, testing, staging, source control, tools, etc.) | Task
eGov |  | Sprint 1 | Sprint planning | Task
eGov |  | Sprint 1 | Daily standup meetings | Task
eGov |  | Sprint 1 | Analysis & Design | Task
eGov |  | Sprint 1 | Development | Task
eGov |  | Sprint 1 | Code review and issues log creation | Task
eGov |  | Sprint 1 | Testing | Task
eGov |  | Sprint 1 | Master data upload in application database | Task
eGov |  | Sprint 1 | Application demo to customer | Task
eGov |  | Sprint 1 | Sprint 1 review meeting | Task
eGov |  | Sprint 1 | Product release | Task
eGov |  | Sprint 1 | Product backlog refinement | Task
eGov |  | Sprint 2 | Sprint planning | Task
eGov |  | Sprint 2 | Daily standup meetings | Task
eGov |  | Sprint 2 | Analysis & Design | Task
eGov |  | Sprint 2 | Development | Task
eGov |  | Sprint 2 | Code review and issues log creation | Task
eGov |  | Sprint 2 | Testing | Task
eGov |  | Sprint 2 | Master data upload in application database | Task
eGov |  | Sprint 2 | Application demo to customer | Task
eGov |  | Sprint 2 | Sprint 1 review meeting | Task
eGov |  | Sprint 2 | Product release | Task
eGov |  | Sprint 2 | Product backlog refinement | Task
eGov |  | Sprint 3 | Sprint planning | Task
eGov |  | Sprint 3 | Daily standup meetings | Task
eGov |  | Sprint 3 | Analysis & Design | Task
eGov |  | Sprint 3 | Development | Task
eGov |  | Sprint 3 | Code review and issues log creation | Task
eGov |  | Sprint 3 | Testing | Task
eGov |  | Sprint 3 | Master data upload in application database | Task
eGov |  | Sprint 3 | Application demo to customer | Task
eGov |  | Sprint 3 | Sprint 1 review meeting | Task
eGov |  | Sprint 3 | Product release | Task
eGov |  | Sprint 3 | Product backlog refinement | Task
eGov |  | Sprint 4 | Sprint planning | Task
eGov |  | Sprint 4 | Daily standup meetings | Task
eGov |  | Sprint 4 | Analysis & Design | Task
eGov |  | Sprint 4 | Development | Task
eGov |  | Sprint 4 | Code review and issues log creation | Task
eGov |  | Sprint 4 | Testing | Task
eGov |  | Sprint 4 | Master data upload in application database | Task
eGov |  | Sprint 4 | Application demo to customer | Task
eGov |  | Sprint 4 | Sprint 1 review meeting | Task
eGov |  | Sprint 4 | Product release | Task
eGov |  | Sprint 4 | Product backlog refinement | Task
eGov |  | Sprint 5 | Sprint planning | Task
eGov |  | Sprint 5 | Daily standup meetings | Task
eGov |  | Sprint 5 | Analysis & Design | Task
eGov |  | Sprint 5 | Development | Task
eGov |  | Sprint 5 | Code review and issues log creation | Task
eGov |  | Sprint 5 | Testing | Task
eGov |  | Sprint 5 | Master data upload in application database | Task
eGov |  | Sprint 5 | Application demo to customer | Task
eGov |  | Sprint 5 | Sprint 1 review meeting | Task
eGov |  | Sprint 5 | Product release | Task
eGov |  | Sprint 5 | Product backlog refinement | Task
eGov |  | Sprint 6 | Sprint planning | Task
eGov |  | Sprint 6 | Daily standup meetings | Task
eGov |  | Sprint 6 | Analysis & Design | Task
eGov |  | Sprint 6 | Development | Task
eGov |  | Sprint 6 | Code review and issues log creation | Task
eGov |  | Sprint 6 | Testing | Task
eGov |  | Sprint 6 | Master data upload in application database | Task
eGov |  | Sprint 6 | Application demo to customer | Task
eGov |  | Sprint 6 | Sprint 1 review meeting | Task
eGov |  | Sprint 6 | Product release | Task
eGov |  | Sprint 6 | Product backlog refinement | Task
eGov |  | UAT & Security Audit | Application workflow demonstration to customer for UAT | Task
eGov |  | UAT & Security Audit | Customer reported defects log creation during UAT | Task
eGov |  | UAT & Security Audit | Customer reported defects fixing and code finalisation | Task
eGov |  | UAT & Security Audit | UAT Signoff from customer | Task
eGov |  | UAT & Security Audit | Application deployment & setup on staging server | Task
eGov |  | UAT & Security Audit | Security audit reported issues resolution by development team | Task
eGov |  | UAT & Security Audit | Security Audit clearance certificate & final report from security auditor | Task
eGov |  | Project Planning & Monitoring | Project Level - Project Management Plan (PMP) documentation | Task
eGov |  | Project Planning & Monitoring | Review & rework on project level - PMP | Task
eGov |  | Project Planning & Monitoring | Project level - PMP document approval | Task
eGov |  | Project Planning & Monitoring | Project details & tasks update in PMS tool | Task
eGov |  | Project Planning & Monitoring | Risk analysis and risk register creation | Task
eGov |  | Project Planning & Monitoring | Project metrices capturing and analysis | Task
eGov |  | Project Planning & Monitoring | Internal meetings, progress reviews & followups with senior management and project team | Task
eGov |  | Project Planning & Monitoring | External meetings & followups with customer & NIC | Task
eGov |  | Project Planning & Monitoring | Status reporting to customer and senior management | Task
eGov |  | Project Planning & Monitoring | PMS tool data updation | Task
eGov |  | Project Planning & Monitoring | Internal audits and reported issues closure | Task
eGov |  | Project Planning & Monitoring | Project backup & restoration related activity | Task
eGov |  | Change Management | Change request analysis, change request form and impact analysis document creation | Task
eGov |  | Change Management | Change request estimation sheet creation | Task
eGov |  | Change Management | Change request approval from HOD (Internal) | Task
eGov |  | Change Management | Change request approval from customer | Task
eGov |  | Change Management | Change request implementation | Task
eGov |  | Change Management | Change request verification & sign-off from customer | Task
eGov |  | Go-Live | Security clearance from Cyber Security Division NIC | Task
eGov |  | Go-Live | Production server setup and configuration | Task
eGov |  | Go-Live | User manual documentation | Task
eGov |  | Go-Live | User manual review & finalisation | Task
eGov |  | Go-Live | User manual approval | Task
eGov |  | Go-Live | Release Notes creation, review and finalisation | Task
eGov |  | Go-Live | Release Notes review and approval | Task
eGov |  | Go-Live | Release audit meeting before production release of application | Task
eGov |  | Go-Live | Release audit issues closure and verification | Task
eGov |  | Go-Live | Go-Live: Application deployment on production server | Task
eGov |  | Go-Live | Go-live signoff from customer | Task
eGov |  | Go-Live | End user training to customer team | Task
eGov |  | Go-Live | User training signoff from customer | Task
eGov |  | Go-Live | Post Go-Live Onsite Support | Task
eGov |  | Project Closure | Project Completion Certificate from Client as per NICSI Format | Task
eGov |  | Project Closure | Bill Submission - NICSI | Task
eGov |  | Project Closure | Project closure sign-off from customer | Task
eGov |  | Project Closure | Project closure checklist execution & issues closure in PMS tool | Task
eGov |  | Project Closure | Lessons learnt & best practices documentation | Task
eGov |  | Project Closure | Project handover to support team | Task