## Waterfall
E-Gov Artifacts List |  |  |  | Version 1.1
Milestone | Activity | Mandatory Artifacts | Desired Artifacts | Responsibility | Execution / Remarks | Mandatory Artifacts Templates
Project Initiation Milestone | Handover to PM from Sales team | 1) Handover Meeting invite 2)Handover MOM |  | 1) HOD 2) PM | 1) Through Email 2) Attach document in PMS Tool
| Internal Project Initiation | 1) Internal Kick off meeting MOM | 1) Internal Kick Off meeting presentation 2) Internal Kick of meeting invite | PM | Attach document/mail in PMS Tool
| External Project Initiation | 1) External Kick Off meeting presentation 2) External Kick off meeting MOM | 1) External Kick of meeting invite | PM | Attach document/mail in PMS Tool
| Estimation Sheet Creation | 1) Estimation sheet (Pre-Sales Team Estimation) 2) Cost estimation 3) Cost & Estimation approval |  | 1) PM & Tech Lead 2) PM 3) HoD/Admin/Mgmt | 1) Estimation Sheet received from Pre Sales Team 2) Update in PMS tool 3) workflow Approval in PMS tool
| Project Schedule (High Level Schedule) | 1) Project schedule in PMS tool (with schedule, efforts and resource allocation) | 1) Schedule approval from HoD and Customer | 1) PM & Tech Lead | 1) Creation of project milestones and tasks with efforts and timeline in PMS tool
Project Planning & monitoring | Project Planning | 1) Project Management Plan- Org level- (Excel format) 2) Project management Plan - Project Level (Excel format) 3) Approval of project level PMP 4) Identification of Life cycle model in PMP or PMS (waterfall or Agile) |  | 1) HOD 2) PM 3) HOD 4) PM | 1) Create PMP - Org level Execel file and upload in PMS Tool 2) PMP - Project level to be created in Excel template and upload in PMS tool 3) To be implemented in Tool 4) To be implemented in Tool
| Create WBS | Create tasks till requirements phase |  | TL & PM | Creation of WBS in PMS tool
| Skill gap analysis | 1) Skill matrix in PMWB or PMS |  | PM & TL | Fill Skill matrix sheet in Project level PMP Excel file and upload in PMS tool
| Training Plan and Tracking (Internal) | 1) Training Plan in PMWB or PMS 2) Updation of training records | Hiring Plan | 1) HoD, TL & HR 2) PM, TL & HR | 1) Fill Training Plan in Project level PMP Excel file and upload the document in PMS tool 2) Attach Emails/Documents in PMS Tool
| Stakeholder List | 1) List of stakeholder 2) Stakeholder involvement 3) Stakeholder dependency |  | 1) PM 2) PM 3) PM | 1) Fill project stakeholders details in PMS Tool 2) Fill required details in PMS tool 3) Column to be added in PMS tool: Stakeholder Dependency (In Progress)
| Assumption and dependency | 1) List of dependencies in project 2) List of assumptions |  | 1) PM 2) PM | Fill project dependencies and assumptions details in PMS tool
| Risk Management | 1) List of risk, risk sources, risk categories 2) Risk analysis 3) Risk Mitigation and Contingency plan |  | 1) PM & Tech Lead 2) PM, Tech Lead & RM 3) PM, Tech Lead & RM | Create project risk register with all required details and upload in PMS tool
| Metrics Analysis | 1) Effort logging in PMS 2) Schedule/Progress updation in PMS 3) Metrics dashboard updation 4)root Cause Analysis for Metrics deviations |  | 1) Project Team 2) PM & TL & QA Lead 3) PMS Tool 4) PM & HOD | 1) Update in PMS Tool 2) Update in PMS Tool 3) Auto Update 4) Corrective actions should be updated in PMS Tool
| Risk Management | 1) Evidence for implementation of Mitigation and Contingency plan 2) Occurred risk to be moved to in project issue list 3) Risk analysis update |  | 1) PM & TL 2) PM & TL & QA Lead 3) PM | 1) Attach document (Email proof/evidence) in PMS Tool 2) Issue update in PMS Tool 3) attach updated document in PMS Tool
| Assumption And Dependencies | 1) Update assumption and dependencies 2) Evidence for tracking of dependencies |  | 1) PM 2) PM | 1) Update in PMS Tool 2) Through Mail (attach)
| Stakeholder Tracking | 1) evidence for involvement of stakeholder 2) Meeting MOMs with stakeholder |  | 1) PM & BA 2) PM & BA | 1) Attach emails in PMS Tool 2) Attach MOM documents in PMS Tool
| Review Project Progress (fortnightly) | 1) Internal meeting MOM | 1) Internal meeting invite | 1) PM & TL | 1) Attach MOM documents in PMS Tool
| Conduct Senior Management Review (monthly) | 1) HoD review MOM | 1) Sr. mgmt. meeting invite 2) Sr. mgmt. presentation | 1) PM & HOD | 1) Attach E-mails/corrective action update in PMS Tool
| Re-Estimation | 1) evidence for re-estimation at milestones 2) Estimation approval |  | 1) PM & TL 2) HOD/Admin/Mgmt. | 1) Attach E-mails/Updated Estimation sheet in PMS Tool 2) Workflow approval in PMS Tool
| Take Backup | Project backup and restoration |  | 1) IT Team/Admin | 1) Email from project team requesting project backup implemention to IT team. Attach confirmation mail from IT team in PMS Tool.
Requirements Development Milestone | Analyse requirements | 1) Query sheet | 1) mail evidence for query and resolution | PM & BA | Filled query log sheet through Email/template.
| Gather Requirements | 1) Any evidence for gathering requirements | 1) Meeting invites 2) and data shared by client 3) client business process | PM & BA | Attach MOM document in PMS Tool
| Validate Requirements | Evidence for requirement validation like joint walkthrough, presentations, prototypes etc. |  | PM & BA | MOM, Workflow Presentation, Mail Invitation, SRS Sign Off
| SRS documentation | 1) Review issues in PMS tool 2) Approval email 3) Approved SRS 4) Updated revision history for SRS | 1) SRS review email 2) resource allocation for SRS review in task list 3) 3) Separate task for SRS review | 1) PM 2) PM 3) PM 4) PM | 1) Document related issue log 2) Only sign off copy is required 3) Attach customer approved SRS document in PMS tool 4) Version wise section update in SRS document
| Prepare Requirement Traceability Matrix | Updated requirement traceability matrix till requirement phase |  | BA & TL | Create RTM sheet till requirements phase and upload in PMS tool
| Estimation Sheet updation | 1) Estimation sheet (size estimation using complexity point method) 2) Cost estimation 3) Cost & Estimation approval | 1) Estimation received from Sales team | 1) PM & Tech Lead 2) PM 3) RM/Admin/Mgmt | 1) Attach estimation sheet in PMS tool 2) Available in PMS Tool 3) workflow Approval in PMS tool
| Revise WBS after re-estimation | Create tasks |  | TL & PM | Revise project WBS in PMS tool after estimation approval
Design Milestone | Evaluate Design Alternatives | DAR for design alternatives | MOM for discussions | Tech Lead & PM (HoD if required for decision) | Create DAR evaluation sheet and attach in PMS tool
| Prepare Technical Design | 1) Technical design document 2) review issues in PMS tool 3) approval email 4) Updated revision history for TDD | 1) TDD review email 2) resource allocation for TDD review in task list 3) Separate task for TDD review | 1) Tech Lead 2) HoD 3) Tech lead 4) Tech Lead | 1) Create technical design document and upload in PMS Tool 4) Versioning update in TDD
| Update Requirement Traceability Matrix | Updated requirement traceability matrix till design phase |  | TL | Update RTM document till design phase and upload in PMS tool
Development Milestone | Develop Code | 1) Wireframes 2)Source code 3) Code review issues in PMS | 1) Coding guidelines 2) Code review email | 1) Designer 2) Developer 3) TL | 1) Wireframes/developed source code should be uploaded in SVN 2) In SVN 3) Perform code review as per code review checklist and Update in PMS Tool
| Unit Testing | 1) Unit testing execution test log 2) Unit test issues in PMS tool |  | 1) Developer 2) Developer | 1) Create separate task in PMS Tool 1.1) Execute through N-Unit/J Unit 2) Update/Attach in PMS Tool
| Update Requirement Traceability Matrix | Updated requirement traceability matrix for source code |  | TL | Update RTM document till development phase and upload in PMS tool
Testing | Test Planning | 1) Test plan 2) review of test plan | 1) Test Plan review email 2) resource allocation for test plan review in task list 3) Separate task for test plan review | 1) QA Lead 2) PM | 1) Create Test Plan in defined template and attach document in PMS Tool 2) Create task in PMS Tool 3) Update in PMS Tool
| Test Cases | 1) Test cases 2) Test Case Review 3) Test results 4) Test issues in PMS tool | 1) Test data | 1) Tester 2) QA Lead 3) Tester 4) Tester | 1) Create test cases in defined template and attach filled test cases document in PMS Tool 2) Create task in PMS Tool 3) Attach document in PMS Tool 4) Update in PMS Tool
| RTM | Updated requirement traceability matrix for test cases |  | QA Lead | Update RTM document till development phase and upload in PMS tool
Acceptance Testing | Provide demo to user before UAT (if applicable) | 1) Meeting invite for demo (if any) 2) Demo issues from user |  | 1) PM & BA 2) BA | 1) Through Email 2) Update in PMS Tool
| Conduct UAT | 1) Meeting invite for UAT 2) UAT issues in PMS as external defects |  | 1) PM & BA 2) BA | 1) Through Email 2) Update in PMS Tool
| UAT Signoff | 1) UAT sign off from user |  | PM & BA | 1) E-mail/Sign Off Document received from customer
Go Live | Release notes | 1) Release notes 2) Release notes approval |  | 1) QA Lead & BA 2) PM | 1) Create release notes document for each customer release in defined template and upload the approved version in PMS Tool 2) Attach Approval Mail
| User manual | 1) User manual 2) User manual approval |  | 1) Tester & BA 2) QA Lead & PM | 1) Create User Manual in defined template and upload in PMS Tool 2) Attach Approval Mail
| Perform Release Audit | 1) Release Audit checklist (Before Go Live) 2) Audit Issues |  | 1) Audit Team 2) Audit Team | 1) Attach Audit Report in PMS Tool 2) Attach updated document in PMS Tool
| Provide Training (if any) | 1) Training records to user |  | 1) PM & BA | 1) Attach Mail/Document in PMS Tool
| Go Live Sign Off | 1) Sign Off Document |  | 1) PM & BA | 1) Attach E-mail/Document in PMS Tool
Change Management | Change Request | 1) Change request logging 2) Impact analysis 3) Estimation for CR (using project method as above) 4) CR implementation 5) CR closure |  | 1) BA 2) HoD, PM & TL 3) PM & TL 4) TL & QA 5) QA & BA | 1) Update in PMS Tool 2) Attach document in PMS Tool 3) Attach document in PMS Tool 4) Create milestone/task in PMS Tool 5) Update in PMS Tool
Internal Audit | Conduct audit (monthly) | 1) Audit report | 1) Audit calendar and invite | 1) Audit Team | 1) Attach Audit Report in PMS Tool
Project Closure Procedure | Project Closure Sign Off | Project Closure Sign Off |  | PM & BA | Attach project closure sign-off Email/Document in PMS Tool
| Update The Project Data | 1) Ensure final Update data in tool |  | 1) PM & TL & QA Lead | 1) Checklist confirmation in PMS Tool
| Project Closure | 1) Lessons learnt and best practices 2) Project Handover to Support | 1) project closure meeting invite and MOM | 1) PM & TL 2) TL & BA | 1) Fill Lessons learnt & Best practices in Project level PMP Excel file and upload the document in PMS tool 2) Update in PMS Tool & Attach Email/Document