## Project Plan
PMS Tool Template for Web Application Project (Waterfall)
Project Group | Project Name | Milestone | Task | Type | effort | Start Date | End Date
eGov |  | Project Initiation | Project handover meeting with HOD | Task
eGov |  | Project Initiation | Project Kick-off meeting (Internal) with project team members | Task
eGov |  | Project Initiation | Project Kick-off presentation (External) creation & finalisation | Task
eGov |  | Project Initiation | Project Kick-off meeting with customer | Task
eGov |  | Project Initiation | Project schedule plan creation in PMS tool | Task
eGov |  | SRS & Home Page Sign Off | Requirements analysis and SRS documentation | Task
eGov |  | SRS & Home Page Sign Off | Home page design layouts creation | Task
eGov |  | SRS & Home Page Sign Off | Home page design approval by customer | Task
eGov |  | SRS & Home Page Sign Off | Final workflow walkthrough & validation with customer | Task
eGov |  | SRS & Home Page Sign Off | SRS review & finalisation by development team | Task
eGov |  | SRS & Home Page Sign Off | SRS approval & Sign-off by customer | Task
eGov |  | SRS & Home Page Sign Off | Requirements Traceability Matrix (RTM) creation & update till requirements phase | Task
eGov |  | SRS & Home Page Sign Off | Estimation sheet creation after SRS approval | Task
eGov |  | SRS & Home Page Sign Off | Estimation sheet review, rework and approval | Task
eGov |  | SRS & Home Page Sign Off | WBS tasks creation and resources assignment in PMS tool for complete development | Task
eGov |  | Design & Development | HTML structure development using approved home page design | Task
eGov |  | Design & Development | Decision Analysis & Resolution (DAR) meeting for design alternatives and evaluation sheet creation | Task | PM
eGov |  | Design & Development | Technical Design Document (TDD) documentation | Task | TL
eGov |  | Design & Development | TDD review and finalisation | Task | PM, TL
eGov |  | Design & Development | Design Integration with application | Task
eGov |  | Design & Development | Modules development & Customisation | Task
eGov |  | Design & Development | Code review and issues log creation | Task
eGov |  | Design & Development | Developed workflow verification by BA and Issues log creation | Task | BA
eGov |  | Design & Development | Unit testing and issues resolution | Task
eGov |  | Design & Development | Requirements Traceability Matrix (RTM) update till Design & Development phase | Task
eGov |  | Testing & Data Upload | Master data tracking sheet creation | Task
eGov |  | Testing & Data Upload | Master collection and structuring | Task
eGov |  | Testing & Data Upload | Master data upload in the application database | Task
eGov |  | Testing & Data Upload | Uploaded master data review, rework on test application | Task
eGov |  | Testing & Data Upload | Test plan creation, review and finalisation | Task
eGov |  | Testing & Data Upload | Test cases creation,review and finalisation | Task
eGov |  | Testing & Data Upload | QC Testing and issues log creation | Task | Tester
eGov |  | Testing & Data Upload | Testing issues fixes verification and closure by testing team | Task
eGov |  | Testing & Data Upload | Testing sign-off & final test report from QC team | Task
eGov |  | Testing & Data Upload | Source code finalisation after testing issues closure by development team | Task
eGov |  | Testing & Data Upload | Requirements Traceability Matrix document update till testing phase | Task
eGov |  | UAT & Security Audit | Application workflow demonstration to customer for UAT | Task
eGov |  | UAT & Security Audit | Customer reported defects log creation during UAT | Task
eGov |  | UAT & Security Audit | Customer reported defects fixing and code finalisation | Task
eGov |  | UAT & Security Audit | UAT Signoff from customer | Task
eGov |  | UAT & Security Audit | Application deployment & setup on staging server | Task
eGov |  | UAT & Security Audit | Security audit reported issues resolution by development team | Task
eGov |  | UAT & Security Audit | Security Audit clearance certificate & final report from security auditor | Task
eGov |  | Project Planning & Monitoring | Project Level - Project Management Plan (PMP) documentation | Task | PM
eGov |  | Project Planning & Monitoring | Review & rework on project level - PMP | Task | PM
eGov |  | Project Planning & Monitoring | Project level - PMP document approval | Task
eGov |  | Project Planning & Monitoring | Project details & tasks update in PMS tool | Task | PM, TL
eGov |  | Project Planning & Monitoring | Risk analysis and risk register creation | Task | PM, TL
eGov |  | Project Planning & Monitoring | Project metrices capturing and analysis | Task | PM, TL
eGov |  | Project Planning & Monitoring | Causal analysis and preventive action identification | Task | PM, TL
eGov |  | Project Planning & Monitoring | Internal meetings, progress reviews & followups with senior management and project team | Task | PM
eGov |  | Project Planning & Monitoring | External meetings & followups with customer & NIC | Task | PM
eGov |  | Project Planning & Monitoring | Status reporting to customer and senior management | Task | PM
eGov |  | Project Planning & Monitoring | PMS tool data updation | Task | PM, TL
eGov |  | Project Planning & Monitoring | Internal audits and reported issues closure | Task | PM
eGov |  | Project Planning & Monitoring | Project backup & restoration related activity | Task
eGov |  | Change Management | Change request analysis, change request form and impact analysis document creation | Task
eGov |  | Change Management | Change request estimation sheet creation | Task
eGov |  | Change Management | Change request approval from HOD (Internal) | Task
eGov |  | Change Management | Change request approval from customer | Task
eGov |  | Change Management | Change request implementation | Task
eGov |  | Change Management | Change request verification & sign-off from customer | Task
eGov |  | Go-Live & Project Closure | Security clearance from Cyber Security Division NIC | Task
eGov |  | Go-Live & Project Closure | Production server setup and configuration | Task
eGov |  | Go-Live & Project Closure | User manual documentation | Task
eGov |  | Go-Live & Project Closure | User manual review & finalisation | Task
eGov |  | Go-Live & Project Closure | User manual approval | Task
eGov |  | Go-Live & Project Closure | Release Notes creation, review and finalisation | Task
eGov |  | Go-Live & Project Closure | Release Notes review and approval | Task
eGov |  | Go-Live & Project Closure | Release audit meeting before production release of application | Task
eGov |  | Go-Live & Project Closure | Release audit issues closure and verification | Task
eGov |  | Go-Live & Project Closure | Go-Live: Application deployment on production server | Task
eGov |  | Go-Live & Project Closure | Go-live signoff from customer | Task
eGov |  | Go-Live & Project Closure | End user training to customer team | Task
eGov |  | Go-Live & Project Closure | User training signoff from customer | Task
eGov |  | Go-Live & Project Closure | Post Go-Live Onsite Support | Task
eGov |  | Go-Live & Project Closure | Completion Certificate from Client as per NICSI Format | Task
eGov |  | Go-Live & Project Closure | Bill Submission - NICSI | Task
eGov |  | Go-Live & Project Closure | Project closure sign-off from customer | Task
eGov |  | Go-Live & Project Closure | Project closure checklist execution & issues closure in PMS tool | Task
eGov |  | Go-Live & Project Closure | Lessons learnt & best practices documentation | Task
eGov |  | Go-Live & Project Closure | Project handover to support team | Task