Estimation Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 5-Nov-14 |  | NA | Initial Version |
| 1.0 | SEPG | 26-Nov-14 |  | NA | baselined |

Purpose:

Purpose of estimation process is to estimate the size to derive the effort, cost and schedule using the estimation methodology and the historical data

| Inputs | Outputs |
| --- | --- |
| - Request for Proposal - Software Requirement Specification - Change Request - Historical data | - Estimation Sheet |

Entry Criteria:

- Project is assigned to Uneecops

- Contract or Request for Proposal is received

- Change Request is received

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Project Manager | Study Requirements Document | Project Manager in discussion with functional consultant/Business Analyst analyses the technical proposal and software requirement specification document. |
| Project Manager | Perform Estimation | Project manager performs estimation at requirements phase end after requirements sign-off from customer and at the time of following- - Change in scope - Change request Project Manager documents the complexity level criteria, elaborates the coding & unit testing activities/tasks WBS, maps each activity with complexity level, sets the effort distribution across phases, assumptions and risk related to the estimation sheet. Project Manager may refer to organisational or project level historical data while conducting the estimation. |
| Project Manager | Add Contingency Factor (Where Applicable) | Project manager identifies contingency factor to the overall estimation. |
| Project Manager | Arrive At Schedule | Based on the estimated effort, project manager arrives at schedule of the project in discussion with Head of department. |
| Project Head | Review And Approve The Estimation | Project head reviews and approves the estimation |

Exit Criteria:

- Estimation is approved and available with project manager for planning project activities

Verification and Validation:

- Review of estimation process by SQA during process compliance audit

Measurements:

- Total size estimated

- Total effort estimated