## Read Me
Read Me
All white cells are editable in the estimation template
Estimation Summary
1 | In this sheet, mention the basic project information.
2 | This sheet gives the amount of effort estimated for each phase, based on the effort distribution.
3 | ‘Engineering effort’ is the total amount of effort estimated for the project
4 | Total Size (complexity Point) is the calculated value of the complex points or the size of the work that has to be performed.
5 | ‘Project Management Effort’ is the percentage of Engineering Effort that will be required for project management.
6 | ‘Total Effort (Hours)’ is the sum of ‘Engineering Effort’ and ‘Project Management Effort’
7 | ‘Contingency %’ is the percentage of total effort that counts for an incidental expense
8 | ‘Grand Total Effort (Hours)’ is the sum of ‘Total Effort (Hours)’ and ‘‘Contingency %’’
9 | ‘Assumptions’ and Risks: List all the assumptions and risks related to estimation
Estimation Criteria
1 | Mention the criteria for various complexities i.e. Low, Medium, High and effort spent in coding phase for each of the complexity.
2 | Mention the effort distribution percentage for each phase.
Estimation Sheet
1 | List down all the functions or requirements to be developed
2 | Identify the complexity in for each functions or requirements to be developed.
3 | For each requirement, coding effort will get populated and we will get the sum of coding effort
Revision History
1 | Details of the revision done to the estimation to be logged in this sheet

## Estimation Summary
Estimation Summary
Project Information
Project Code | Project Name
Estimated By | Estimation Date
Reviewed By | Review Date
Approved By | Approval Date
Effort Distribution
Phases | % Effort | Efforts
Requirement Development Phase | 20 | 24
Design Phase | 10 | 12
Coding and Unit Testing Phase | 30 | 36
Testing Phase | 5 | 6
User Acceptance Testing | 10 | 12
Certification Testing Phase | 10 | 12
STQC Phase | 10 | 12
Go-Live | 5 | 6
Total Engineering Effort (Hours) | 100 | 120
Total Size (complexity Point) |  | 18
Productivity Factor (CP per Hour) |  | 0.15
Miscellaneus Effort |  | 120
Project Management and Support Activities Effort |  | 0.1
Total Effort (Hours) |  | 264
Contingency % |  | 20%
Grand Total Effort (Hours) |  | 316.8
Assumptions
Risks

## Calculation (hidden)
S.No | Factors | Value
1 | Application Complexity | #REF! | #REF!
2 | Clarity of the design / architecture | #REF! | #REF!
3 | Application Experience | #REF! | #REF!
4 | Project Experience | #REF! | #REF!
5 | Tools involved | #REF! | #REF!
6 | Domain Knowledge | #REF! | #REF!
7 | Platform / Language Experience | #REF! | #REF!
8 | Documentation to be created | #REF! | #REF!
9 | Reusability | #REF! | #REF!
#REF!
| Total Size | #REF!

## Estimation Criteria
Estimation Criteria Setup
| Criteria | Effort in Coding Phase | Normalisation | Count of H/M/L | Total Size
Low | ABC | 2 | 1 | 13 | 13
Medium | XYZ | 3 | 1.5 | 2 | 3
High | PQR | 4 | 2 | 1 | 2
|  |  |  | Total Size | 18
Effort Distribution
Phases | % Effort
Requirement Development Phase | 20
Design Phase | 10
Coding and Unit Testing Phase | 30
Testing Phase | 5
User Acceptance Testing | 10
Certification Testing Phase | 10
STQC Phase | 10
Go-Live | 5
Total | 100

## Estimation Sheet
Estimation Sheet
Module Name
Functions
S. No | Function No. | Function Name | Complexity | Estimated Coding Effort
|  | A | Low | 2
|  | B | Low | 2
|  | C | High | 4
|  | D | Low | 2
|  | F | Low | 2
|  | G | Low | 2
|  | H | Medium | 3
|  | I | Medium | 3
|  | J | Low | 2
|  | K | Low | 2
|  | L | Low | 2
|  | M | Low | 2
|  | N | Low | 2
|  | O | Low | 2
|  | P | Low | 2
|  | A | Low | 2
|  |  | Sub Total | 36

## Miscellaneous Effort
Miscellaneous/Other Tasks
Estimate the effort for miscellaneous/other tasks (like UAT support, User Training etc.) (Both Engineering and Non-Engineering)
S. No | Miscellaneous/Other Tasks | Effort (Hours)
1 | User training | 100
2 | Installation | 20
3
4
5
6
7
8
9
10
| Total Miscellaneous/Other Effort (PH) | 120

## Cost Estimation
Cost Estimation
Direct Cost |  |  |  |  | In-Direct Cost
Location | Cost/Hr | Resource Type | Total Effort (in person hours) | Resource Cost | Parameter | Cost
Onsite | 100 | PM | 25 | 2500 | Travel cost
Off-on | 80 | FC | 20 | 1600 | External consultant charges
Onsite | 50 | TC | 20 | 1000 | Insurance charges
Offshore | 50 | Dev | 20 | 1000 | Specific software cost
|  |  |  | 0 | Travel allowance
|  |  |  | 0 | Travel cost
|  |  |  | 0 | Training cost
0
Total Resource Cost |  |  |  | 6100 | Total Indirect Cost | 0
Total Cost Estimate |  |  |  |  | 6100

## Revision History
Revision History
Ver. No. | Date | Prepared by/Modified by | Significant changes | Approved By