## Template Revision History
Revision History
Version | Baseline Date | Change Description | Author | Reviewed By | Approved By
Name & Title

## Audit checkpoints
Process Compliance Checklist |  |  |  | V1.4
Project Code
Project Name
PM Name
Auditor Name
Audit Date
Current Phase of project
Effort Spent
S.No | Checkpoint | Yes/No/NA | Remarks
A | Project Initiation
1 | Is project handover meeting conducted with HOD and minutes captured in MOM document? | NA
2 | Have project related documents from Pre-sales team (such as Tender/TOR, approved technical proposal, work order/Purchase Order, estimation sheet) handed over to PM? | NA
3 | Are project handover meeting findings/action items tracked to closure? | NA
4 | Has internal kick-off meeting with project team members been performed using presentation PPT and MOM created? | NA
5 | Has external kick-off meeting with customer team been performed using project kick-off presentation and minutes captured in MOM document? | NA
6 | Has MOM document for project kick-off meeting with customer, been shared through email to all participants (customer, internal management team and project team members)? | NA
7 | Are project details and schedule plan containing milesones/tasks with effort, timeline & resources allocation, available in PMS tool? | NA
8 | Is approved org-level project management plan (PMP) document available with all relevant sections appropriately filled up? | NA
9 | Are project Tender/TOR, approved technical proposal, work order/Purchase Order, estimation sheet, kick-off presentation, MOM, Org-level project management plan documents uploaded in PMS tool? | NA
B | Project Planning and Monitoring
10 | Are Estimation/ Re-estimations done based on the estimation guidelines defined in Org-level PMP document? | NA
11 | Are reviews of estimations done and relevant review records available? Are estimations/ re-estimations approved by HOD and top management? | NA
12 | Is Project planning in project-level PMP complete with all relevant sections appropriately filled up? | NA
13 | Are WBS milestones and tasks defined in PMS tool? | NA
14 | Does project-level PMP define applicable life cycle model that reflects the actual practice in the project? Are tailoring details for the project documented? | NA
15 | Is project-level PMP document baselined after approval by HOD? | NA
16 | Is project-level PMP being updated periodically based on triggers? | NA
17 | Are planned parameters like size, schedule, effort, Risks, Issues, defects being tracked at regular frequency as defined in the project-level PMP? | NA
18 | Is metrics data being analyzed and actions taken for any variations are logged under metrics in PMS tool? | NA
19 | Are manpower requirements planned? Are skill & knowledge requirements identified in project-level PMP/PMS tool? | NA
20 | In case of skills gap, training needs & skill upgradation mechanisms are identified as per plan and being tracked? | NA
21 | Are Project assumptions and dependencies details updated in PMS tool? | NA
22 | Are project's stakeholder details (list, involvement and dependencies) updated in PMS tool? | NA
23 | Are project risks being identified, documented and analyzed properly in project risk register? Have stakeholders responsible to take actions for mitigation been informed? | NA
24 | Is filled risk register document uploaded in PMS tool? Are identified mitigation plans/actions being implemented and tracked to closure? | NA
25 | Are project progress review meetings being performed as per defined frequency? Are action items of review meetings being captured and tracked to closure? | NA
26 | Are senior management review meetings being performed at defined frequency and presentation PPT uploaded in PMS tool? Are action items identified being captured and tracked to closure? | NA
27 | Are project actual efforts and schedule being updated in PMS tool? | NA
28 | Are project issues logged in PMS tool and being tracked for closure? | NA
29 | Has project objectives for QPPO (Quality and Process Performance Objectives) been set? | NA
30 | Are identified sub-processes (for the achievement of QPPO), planned and monitored for planning, monitoring and closure phases of the project? It should be based on the defined prediction model in PPM sheet. | NA
31 | Are Org-level initiatives implemeted at project level? Please refer OPM sheet for identified initiatives. | NA
32 | Is process composition done at project level to meet QPPOs? | NA
33 | Is stability and capability analysis done at project level for critical X factors? | NA
34 | Are critical defect types identified at project level or referred from organisation level, and actions implemented? Project level CAR (Causal Analysis & Resolution) sheet should be evidenced. | NA
35 | Is effectiveness of actions on critical defects types evaluated at project level? | NA
C | Software Engineering
36 | Has HTML review checklist been filled by UI design team for created HTML pages of approved UI design and validated by QC team before starting the development of related features? | NA
37 | Have requirements been elicited to define required workflows? Are records of requirements gathering and elicitation from users available? | NA
38 | Is requirement document (SRS) created, reviewed, approved by technical head? Are all review comments being tracked to closure? | NA
39 | Is requirement document approved by customer and baselined? | NA
40 | Has DAR (Decision Analysis & Resolution) evaluation been performed and evaluation sheet uploaded in PMS tool? | NA
41 | Is technical design document (TDD) created, reviewed, approved and baselined? Is TDD uploaded in PMS tool? | NA
42 | Is coding done in accordance with the baselined design documents and coding guidelines? Is code review done using code review checklist and review comments tracked to closure? | NA
43 | Change to Requirements (CRs) are adequately logged, analyzed, estimated, approved and tracked to closure? Is Impact analysis, change proposal, change execution done as per defined process? | NA
44 | Is metrics data being analyzed Is root cause identified or actions taken for any variations are logged under metrics.
45 | Is Unit testing being conducted, testing issues being logged in PMS tool and tracked to closure? | NA
46 | Are test plan and test cases prepared, reviewed , approved & baselined? Is test plan review checklist and test case review checklist used for review? | NA
47 | Is QC testing conducted and all testing issues logged in PMS tool and tracked to closure? | NA
48 | Has QC testing of website/application been completed with all reported issues fixed and signed-off by QC lead? In case of "YES", QC testing sign-off email from QC lead with attached filled QC testing completion report should be available. | NA
49 | Are all customer reported UAT defects logged in PMS tool and tracked to closure? | NA
50 | Are all Security audit defects logged and tracked to closure? | NA
51 | Are all STQC testing defects logged and tracked to closure? | NA
52 | Is Requirements traceability matrix (RTM) created and updated throughout all phases including change requests. | NA
53 | Are release notes being created and reviewed for customer releases? | NA
54 | Are user documentation prepared, reviewed, approved and baselined? | NA
D | Support Activities
55 | Is directory structure for configuration items identified? Is naming convention and labeling mechanism identified? | NA
56 | Are Configuration Audits being done as per audit frequency defined in PMP document and reported issues are logged and tracked to closure? | NA
57 | Is backup of data pertaining to CI items being done at the defined frequency? Are Random restoration checks of backups done? | NA
58 | Has release audit been performed before production release of website/application? Are reported issues logged in PMS tool and tracked for closure before release? | NA
59 | Are corrective action for Non compliances reported during process reviews and release audit identified logged and tracked to closure? | NA
E | Project Closure
60 | Has project level PMP been updated with lessons learnt and best practices details are uploaded in PMS tool? | NA
61 | Has project closure meeting been performed and MoM documented? | NA
62 | Is PMS tool updated with complete project data? | NA
| Count of Yes | 0
| Count of No | 0
| Count of NA | 61
| Process Compliance Index | #DIV/0!