## Process Compliance Checklist
Process Compliance Checklist
Project Code
Project Name
PM Name
Auditor Name
Audit Date
Effort Spent
S.No | Checkpoint | Yes/No/NA | Remarks
A | Project Initiation and Planning
1 | Is the project initiation report prepared? Are all stakeholders informed about the project initiation and initiation meeting conducted. Are all the action items from initiation meeting tracked to closure? | Yes
2 | Is the project initiation review conducted and findings tracked to closure? | Yes
3 | Is the deviation request form prepared and approved for any process tailoring and deviation identified in the project? | NA
4 | Are Estimation/ Re-estimations done based on the estimation guidelines and a methodology defined in PMP? | NA
5 | Are the reviews of estimations are done and relevant review records are available. Are estimations/ re-estimations approved by User or sponsoring directorate? | NA
6 | Estimation are revisited at phase ends and for change in scope? | Yes
7 | Is Project planning (PMP ) complete with all relevant sections appropriately filled up? | Yes
8 | is the work breakdown structure is used for detailing the work for the purpose of estimation & planning? | Yes
9 | Does the PMP define the applicable life cycle model that reflects the actual practice in the project. Are the tailoring details for the project documented? | Yes
10 | Is PMP peer reviewed and review records available? Are all review comments logged & tracked to closure? Is the Project planning checklist used for review? Is PMP baselined based on approval by HOD? | Yes
11 | PMP is updated periodically based on triggers. | Yes
B | Project Monitoring and Control
12 | Are planned parameters like size, schedule, effort, Risks, Issues, defects tracked at regular frequency as defined in the PMP. Is the tracking done quantitatively wrt to defined goals? | Yes
13 | Is the metrics data analyzed and actions taken for any variations in the metrics in PMWB? | Yes
14 | Are human resource requirements planned. Is the Skill & knowledge requirements are identified in PMP/PMWB? Where skills gaps exists, training needs & skill up gradation mechanisms are identified as per plan and tracked? | Yes
15 | Are hardware , software and network resources available as per plan? | Yes
16 | Are the risks relevant to the project are identified appropriately, documented and analyzed. Are stakeholders responsible to take actions for mitigation been informed. Have mitigation actions implemented and tracked to closure. | Yes
17 | Has the project progress review meeting held at the defined frequency? Are action items identified are tracked to closure? | Yes
18 | Has the senior management review meeting held at the defined frequency? Are action items identified are tracked to closure? | Yes
C | Engineering
19 | Have the requirements been elicited to define expectations? Are records of requirements gathering and elicitation from users available? | Yes
20 | Is the requirement (SOW, SRS, BBD) document prepared, reviewed, approved and baseline? Are all review comments tracked to closure? | Yes
21 | Is the requirement document approved by user? | Yes
22 | Change to Requirements (CRs) are adequately logged, analyzed and tracked to closure? Is the Impact analysis, change proposal, change execution is done as per the processes? | Yes
23 | Are the architecture and design specification are prepared, reviewed, approved and baselined? | Yes
24 | Is the coding is done in accordance with the baselined design documents and coding guidelines? Is the code review done using code review checklist and review comments tracked to closure? | No
25 | Are the unit test cases prepared, reviewed , approved & baselined. Is the test case review checklist used for the review? | No
26 | Is the Unit Testing conducted and all testing observations are tracked to closure? | No
27 | Are the Test plan and test cases prepared, reviewed , approved & baselined? Is the test plan review checklist and test case review checklist used for the review? | No
28 | Is the testing conducted and all testing observations are tracked to closure? | Yes
29 | Are all UAT defects logged and tracked to closure? | Yes
30 | Are all Security testing defects logged and tracked to closure? | Yes
31 | Are all STQC testing defects logged and tracked to closure? | Yes
32 | Is the Requirements traceability matrix is established and maintained (including CRs), through out all phases. | Yes
33 | Are user documentation prepared, reviewed, approved and baselined? | Yes
D | Support
34 | Is configuration status report updated for all CIs? Are access rights provided to team as per access rights form? Is backup of data pertaining to CI items are done at the defined frequency? Are Random restoration checks of backups done? Are CM audits done in accordance with the audit frequency defined in PMP? | No
35 | All releases are subjected to release audit as defined in PMP? | No
36 | Are corrective action for Non compliances reported during process reviews and release audit identified and tracked to closure? | Yes
E | Project Closure
37 | Has the project been closed as per QMS process. Has the virtual closure done for projects running more than 6 months? Is the closure report complete with lessons learnt, best practice and project closure meeting conducted? | No
38 | Is the Risk database, Metrics database, Learning database updated with project risk data and shared with organization? | NA
| Count of Yes | 27
| Count of No | 7
| Count of NA | 4
| Process Compliance Index | 79.4118

## Scoring Criteria
Process Compliance Index = Total No. 'YES'/(Total No. of 'YES' + Total No. of 'NO')
PCI Score | RAG Status
Pci Score 80 -100
Pci Score >50 - <80
Pci Score <50