Quantitative Project Management

Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 1.0 | SEPG | 04-Jan-18 | Manoj Nagpal | NA | Initial Version |

- Purpose

The purpose of Quantitative Project Management (QPM) is to quantitatively manage the project’s defined processes and objectives.

The Quantitative Project Management process involves:

    - Establishing and maintaining the project’s objectives at project level.

    - Identifying lifecycle process and components that will be required to meet the project objectives.

    - Monitoring the sub process attributes by suitable statistical or quantitative techniques.

    - Taking decisions in the project based on prediction result and actual result.

    - Identify and take corrective actions to positively impact the ability of the project to meet its objectives.

- Inputs

- PPMs released by SEPG team.

- Entry Criteria

- PPM and PPBs are released.

- Project has been formally initiated.

- Tasks

  - Setting up project objectives

- At the start of the project, project manager prepares a plan for quantitatively managing the project & documents the same in the project management plan. Project manager:

    - Identifies the critical objectives of the project.

    - Assigns the relative priorities of the objectives based on the customer, the organizational business objective, and the project requirement.

- For each of the identified project objectives, project manager identifies the metric that will be used to ensure and monitor the objectives.

- Project manager sets the targets for these objectives. The targets are based on actual historical performance referred from the baselines or based on customer expectations, if any.

- These are documented in the measurement framework which also contains the operational definition, source of metrics, measures required, collection and analysis technique.

- In situations, when the metrics targets in the service level are significantly different / tailored from organization goals rationale for the difference is documented in the metrics plan. An approval is expected to be taken from the project head.

  - Establish project lifecycle and identify applicable sub process

- Project manager based on the SDLC, identifies the relevant prediction model to be used in the project.

- The project manager identifies the various alternative methods in the processes available in the organization for executing the project.

- Project manager performs the process composition using the relevant PPM to select the optimal set of sub process and relevant statistical methods that balances and best meet the critical project objectives.

- The results of this analysis is documented in the PPB workbook or Predictive modelling template.

- In case the best options still fall short with respect to the overall certainty of meeting the service objective, a risk with appropriate mitigation plans also needs to be identified and reported to project head.

  - Identify critical sub processes for statistical management

- Based on the composed sub processes, the sub processes for statistical monitoring and control are identified. These critical sub processes will be taken up for control using the appropriate statistical techniques.

- Based on the sub process performance or historical information available, objectives specific to sub processes can be set by the project manager to assess the capability of the sub process.

  - Monitoring overall project performance

- Statistical and quantitative techniques are used to monitor the performance of the sub process through its critical attributes during the course of the project using PPM workbook.

- As the project progresses, the actual performance of the sub processes are fed into the model and the results re-predicted for the service.

- The output from the model as part of prediction is used for evaluating the progress of the project with respect to its initial objectives and if required for reconciliation (revision) of project management Plan.

- In cases when the results still shows that the project will be missing its objective then risks about not achieving project objectives is identified and reported to relevant stakeholders. Appropriate corrective actions are planned and monitored till closure  This may involve

    - Initiating improvements in the sub process performance. Refer CAR process for the details.

    - Rerunning the PPM to recompose the processes for the remaining part of the lifecycle.

    - Renegotiating targets and taking approval from the appropriate stakeholders.

- Prediction results, sub process performance limits as well as the improvements initiated are reported in project reviews with senior management

  - Monitoring critical sub process performance

- The performance of the critical sub processes is monitored during its execution and is tracked against its objectives. Typically control charts are used for the monitoring.

- The stability of the critical sub process is analyzed using the control chart rules of stability. The capability is analyzed by comparing with the targets set for the sub process.

- If the sub-process is unstable, CAR is initiated and tracked to closure.

- The results of monitoring are analyzed and reported to relevant stakeholders as appropriate.

- Risks during service execution about not achieving service objectives are identified and reported to relevant stakeholders. Appropriate corrective actions are planned and monitored till closure  This may involve

    - Initiating improvements in the sub process performance. Refer CAR process for the details.

    - Renegotiating targets and taking approval from the appropriate stakeholders.

  - Improve sub process performance

- During execution and continuous monitoring of the sub process the project manager identifies the area for improving the sub process.

- Outliers in the process execution are identified using the rules of control charts and systematically analyzed using structured techniques. On the identification of the causes, actions are identified and taken to remove the cause and increase the stability of the sub process

- A formal analysis is also triggered in case the limits of the process performance are wider than expectation.

- Appropriate corrective actions and preventive actions are planned and monitored till closure

- After suitable time interval, statistical tests are performed to determine the effectiveness of actions and the change in the process performance. In case of statistically significant change, the sub process is re-baselined. The new baselines are to be used in the PPM for re-forecasting using the improved process performance.

- Outputs

- PPM implementation and effectiveness checks.

- Exit Criteria

- Process performance model are implemented.

- Verification

- Verification of the PPM is done based on the actual efforts taken from the project.

- KPIs

- NA.