Metrics Procedure

Revision History

| Version | Updated By | Date | Approved By | Change Request ID | Significant Changes |
| --- | --- | --- | --- | --- | --- |
| 0.1 | SEPG | 5-Nov-14 |  | NA | Initial Version |

Purpose:

This purpose of this process is to identify, track and analyse metrics project level and manage corrective actions till closure

| Inputs | Outputs |
| --- | --- |
| - Any user/stakeholders specific objectives - Organisational level measurement framework | - Update PMWB - Metrics Review Checklist |

Entry Criteria:

- Project lifecycle identified

- Project Initiation meeting conducted, for planning of metrics in the project level

Steps:

| Responsibility | Action | Description |
| --- | --- | --- |
| Project Manager | Identify Project Metrics | Project manager identifies project metrics in the project management plan (PMP) using organisational level measurement framework, based on the project life cycle. In case, metrics are defined by user or there are some project specific metrics, identify those l metrics along with organisational level metrics. |
| Project Manager | Set Metrics Goal | Project manager set metrics goal by referring to organisational metrics baseline report and user/stakeholders specific requirement or project can take project specific goals. Incase project specific goals are lenient from the organizational goals, due approval is required to be taken from HOD. |
| Project Manager | Collect Metrics Data | Project manager collect metrics data for all the planned metrics and update the same in PMWB. Project manager verifies and validates data for completeness, correctness and accuracy. |
| Project Manager | Analyze Metrics Data | Project manager analyze metrics data to identify the deviations (if any). Metrics data is analyzed by comparing the metrics values against the USL and LSL of the metrics. In case there are deviation from the project goals, project manager determine the cause of deviation and identify corrective action and track it to closure in PMWB |
| Project Manager | Review Project Progress | Project manager get the progress of project and metrics reviewed with Sr. Management on periodic basis |
| Project Manager | Submit Metrics Data To The Organizational | At the end of the project, project manager submit metrics data to the organizational repository, as required by the SEPG |

Exit Criteria:

- Project closure

- Project data collected and updated in metrics repository

Verification and Validation:

- Review of project data using metrics review checklist

Measurements:

- Effort spent on metrics data collection and analysis activities