## BO-PO Mapping
Measurement Framework
Business Objectives | Project Objectives
Improve User Satisfaction | On Time Delivery
Better Product Quality
Improve Cost Control | On Time Delivery
Better Product Quality
Increased Productivity
Increase Knowledge Index | Increased Productivity

## Measurement Framework
Measurement Framework
S. No. | Project Objectives | Priority of Project Objectives | Information Need | Metrics | Unit of measure | Calculation Formula | Base Measures | Unit of Base measure | Source Of Data | Analysis Method | Data Collection Frequency | Data Analysis Frequency | Data Reporting Frequency | Responsibility for Data Analysis and Reporting | Project Applicability | Inclusions | Exclusions | Metrics Goals
1 | On Time Delivery | Medium | To ensure that delivery is within initial estimated efforts | Effort Variance Initial (Eva) | % | Effort (Actual) – Effort (Estimated) / Effort (Estimated) * 100 | Initial estimated Effort Actual effort | Man Hours or Person Hours | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Engineering Effort =Total (Requirement + Design + Coding +Testing + Delivery + Acceptance Testing) phase effort PM Effort= Project initiation + planning + Monitoring & Control + closure + SQA effort + training Effort | User Training effort | USL: 20% Goal: 0% LSL:-20%
2 |  | High | To ensure that delivery is within latest baselined efforts | Effort Variance Baseline (Evb) | % | Effort (Actual) – Effort (Revised)/ Effort (Revised)*100 | Effort | Man Hours or Person Hours | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Engineering Effort =Total (Requirement + Design + Coding +Testing + Delivery + Acceptance Testing) phase effort PM Effort= Project initiation + planning + Monitoring & Control + closure + SQA effort + training Effort | User Training effort | USL: 20% Goal: 0% LSL:-20%
3 |  | Medium | To ensure that delivery is within initial estimated schedule | Schedule Variance Initial (Sva) | % | (Actual Completion date – Estimated Completion date) / (Estimated Completion date - start date) * 100 | Actual Completion date Planned start date and Estimated Completion date | Date | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Engineering Schedule =Total (Requirement+ Design+ Coding +Testing + Delivery + Acceptance Testing) phase start and end dates PM Schedule= Project initiation + planning + Monitoring & Control l+ closure + SQA + training start and end dates | User Training Schedule | USL: 20% Goal: 0% LSL:-20%
4 |  | High | To ensure that delivery is within latest baselined schedule | Schedule Variance baseline (SVb) | % | (Actual Completion date – Revised Completion date) / (Revised Completion date - Estimated Start Date) * 100 | Schedule | Date | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Engineering Schedule =Total (Requirement+ Design+ Coding +Testing + Delivery + Acceptance Testing) phase start and end dates PM Schedule= Project initiation + planning + Monitoring & Control l+ closure + SQA + training start and end dates | User Training Schedule | USL: 20% Goal: 0% LSL:-20%
5 |  | Medium | To ensure that support is provided in lesser time | Mean Time To repair (MTTR) | Hours | TTR = (Time when Support ticket t is closed - Time at which Support ticket is received) / Total No. of Support ticket in a period. MTTR = Mean of TTR | Support ticket resolved in a period Total no. of Support ticket in a period | Date | PMWB | Comparison with metrics goals (USL and LSL) | Weekly | Fortnightly | Monthly | PM | Support | Closed Support ticket | Resolution time (TTR) does not include hold time /clarification time | NA
6 | Better product Quality | High | To ensure that lesser number of defects are delivered to user/stakeholder | Defect Removal Efficiency (DRE) | % | DRE= (E/ E+D) *100 where E = Pre-delivery defects ( defects detected during all review and testing activities D= Post – delivery Defects | No of internal and External Defects | No. of defects | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Defects received (including internally found and user/stakeholder reported on interim & final deliverables). In case, testing is done by external agency, the defects reported will be considered at post delivery or external defects | Defects on non-engineering deliverables e.g.: contract, PM, CM, SQA, Suggestion & complaints, Change to work requests Defects found after UAT signoff | USL: 100% Goal: 80% LSL:70%
7 |  | High | To ensure that maximum number of defects are reported during reviews than testing | Review Effectiveness (RE) | % | (No. Of Defects found in Review (before delivery)) / (Total No. Of Defects found before Delivery (both Reviews and Testing)) * 100 | No of internal review and testing Defects | No. of defects | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Only internal defects Only Engineering artifact review defects | External defects Defects on non-engg deliverables e.g.: contract, PM, CM, SQA, Suggestion & complaints, Change to work requests | USL: 70% Goal: 60% LSL:50%
8 |  | High | To ensure that maximum number of defects are reported during internal testing than external testing | Testing Efficiency (TE) | % | (No of Defects found during Testing before delivery / Total No. Of testing Defects (before Delivery + user/stakeholder reported) ) * 100 | No of internal and External testing Defects | No. of defects | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | All defects in testing phase In case, testing is done by external agency, the defects reported will be considered at post delivery or external defects | Defects found after UAT signoff | USL: 100% Goal: 80% LSL:70%
9 |  | High | To ensure that there are lesser number of defects overall | Defect Density (DD) | No. of Defects/Actual Size | (Defects detected in all the phases phase/total actual size)*100 | Total Number of Defects Actual Size | No. of defects Complexity Point | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | Total engineering artifact review and Testing Defects | Defects found after UAT signoff | NA
10 |  | Medium | Number of tickets reopened due to incorrect or incomplete closure | Re-open % | % | Number of Support Ticket reopened in a period/ total no of Support ticket in a period*100 | Support ticket reopened in a period Total no. of Support ticket in that period | Count of maintenance requests | PMWB | Comparison with metrics goals (USL and LSL) | Weekly | Fortnightly | Monthly | PM | Support | Closed and reopened Support ticket | NIL | NA
|  | High | To ensure that defects are identified is stipulated time. | Defect Rate | No. of Defects/Actual Effort | (Total Defects detected in all the phases phase/total actual effrot)*100 | Total Number of Defects Actual Effort | No. of defects Effort | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the phase/milestone/Project | Monthly | PM | Development, Implementation | All defects
11 |  | Low | To ensure lesser requirement change in the project | Requirement Stability Index (RSI) | % | (1- (No. Of ADDED + DELETED + MODIFIED Requirements)/ (total number of initial baselined requirements)) * 100 | Requirements | Count | Project Specific Xls | Comparison with metrics goals (USL and LSL) | Weekly | Fortnightly | Monthly | PM | Development, Implementation | 1. Change in Requirements at all the phases 2. Initial Baselined requirement includes only original set of requirements which were baselined. 3. No. of requirements should be based on the traceability matrix | Defects | Refer PPB
12 | Better product Quality/On Time Delivery | High | To ensure process compliance in the project | Process Compliance Index (PCI) | % | Number of ‘Yes’ in process compliance checklist*100/ (Number of ‘Yes’ in process compliance checklist+ Number of ‘No’ in process compliance checklist) | Count of 'Yes', 'No' in PCI checklist | Count | PCI Checklist | Comparison with metrics goals (USL and LSL) | Monthly | Monthly | Monthly | PM | All projects | Count of 'Yes', 'No' in PCI checklist | NA' in PCI Checklist | USL: 100% Goal: 80% LSL:50%
13 | Better product Quality/On Time Delivery | Low | To ensure process improvement | Number of improvements implemented | Count | Count of number of process improvement implemented in a given period | Number of process change request are implemented | count | Process change request log | NA | Monthly | Quarterly | Quarterly | PEG Head | PEG team | All process change request accepted and implemented | NA | NA
14 |  | Low | To ensure process compliance in the project | Average Non-Compliance Per Project | Count | Total Number of noncompliance reported in the given period/Total Number of projects audited in the given period | Non Compliance | Count | Project Specific Xls | Comparison with metrics goals (USL and LSL) | Monthly | Monthly | Monthly | SQA Head | SQA Team | Non Compliances | NIL | NA
15 | Increase Productivity | High | To ensure that project is delivered in planned Budget | Cost Variance | % | Cost (Actual) – Cost (Revised) / Cost (Revised)* 100 | Revised Cost Actual Cost | Rupees | PMWB | Comparison with metrics goals (USL and LSL) | Fortnightly | Monthly At the end of the phase/milestone/Project | Monthly | PM | All projects | NIL | NIL | USL: 10% Goal: 0% LSL:-10%
16 |  | Low | To ensure coverage of resources | Training Coverage % | % | No. of resources completed the prescribed or mandatory training*100/Total No. of Resources to whom the training has to be imparted | No of resources trained in a particular training | No of resources | Training database | Comparison with metrics goals (USL and LSL) | Quarterly | Quarterly | Quarterly | Training Head | Training Team | Mandatory Trainings | Optional Trainings | USL: 100% Goal: 80% LSL:70%
17 |  | Medium | To ensure the efficiency of the project team | Productivity | Size/Effort | Actual Size/Total Actual Effort spent (in Phrs) | Efforts Size | Man Hours or Person Hours Complexity Point | PMWB | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the project | At the end of the project | PM | Development, Implementation | Engineering Effort | PM Effort | NA
18 | NA | NA | To ensure that delivery is within latest baselined efforts | Requriement Analysis Effort% | Effort% | Actual effrot in Requirement Analysis/Total Actual Effort spent in Requirement phase (in Phrs) | Effort | Man Hours or Person Hours | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the requirement milestone | At the end of the milestone | PM | Development, Implementation | Engineering Effort | PM Effort | Refer PPB
19 | NA | NA | To ensure that delivery is within latest baselined efforts | Design Integration with application Effort% | Effort% | Actual effrot in Design Integration with application/Total Actual Effort spent in design and development phase (in Phrs) | Effort | Man Hours or Person Hours | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the design and deveopment milestone | At the end of the milestone | PM | Development, Implementation | Engineering Effort | PM Effort | Refer PPB
20 | NA | NA | To ensure that delivery is within latest baselined efforts | Module Development Effort% | Effort% | Actual effrot in Module development/Total Actual Effort spent in design and development phase (in Phrs) | Effort | Man Hours or Person Hours | PMS | Comparison with metrics goals (USL and LSL) | Weekly | fortnightly At the end of the design and deveopment milestone | At the end of the milestone | PM | Development, Implementation | Engineering Effort | PM Effort | Refer PPB